TASK DESCRIPTIONS

Investment Simulation Web Application

Version 1.0 — All 58 WBS Tasks

For each task: Objective · Tools · AI Prompts · Input Assumptions · Output Assumptions

Based on Approved Project Plan v1.0

| Property | Value |
| --- | --- |
| Status | Reference Document — Not for Sign-Off |
| Total Tasks | 58 (Phases 0 through 7) |
| Solo Developer | Full-time, AI-Assisted |
| Start Date | March 1, 2026 |
| Target End | ~May 5, 2026 (40.5 working days) |
| Prepared By | Development Team |

# How to Use This Document

Each task entry in this document follows a consistent structure:

| Section | Contents |
| --- | --- |
| OBJECTIVE | What must be accomplished — specific deliverables and acceptance criteria |
| TOOLS | Software tools, CLIs, frameworks, and services used in this task |
| AI PROMPTS | Suggested prompts to use with Claude to accelerate the task — copy, adjust, and use |
| INPUTS | Assumptions about what must be in place before this task can begin |
| OUTPUTS | Assumptions about what the task produces — verification criteria |

AI prompts are starting points. Review and adjust every AI-generated output before committing it. The prompts assume the full project context described in the Technical Specification and Project Plan documents.

Phase 0 · Setup 8 tasks · Mar 01 – Mar 10, 2026

## 0.1  Create GitHub Repository

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 0 · Setup | 0.1 | 0.5 days | Mar 03, 2026 | GitHub.com |

| OBJECTIVE | Create the central version control repository that will host all application source code, documentation, diagrams, and configuration files for the duration of the project. Establish the branching strategy defined in the Technical Specification. - Repository name: investsim (or as agreed with stakeholder) - Visibility: Private during development; may be made public after classroom deployment - Branches to create: main (production), develop (integration) - Apply a Node.js .gitignore template to exclude node_modules, .env, and build artefacts - Add an initial README.md placeholder |
| --- | --- |

| TOOLS | - GitHub.com — repository creation via web interface - Git (command line) — initial clone, branch creation, first push - VS Code — open cloned repository as workspace Prompt: No AI assistance required for this task — it is a manual console operation. |
| --- | --- |

| AI PROMPTS | No AI prompts required for this task. Repository creation is a manual GitHub console operation. AI assistance begins with task 0.2. |
| --- | --- |

| INPUTS | Assumption: GitHub account exists and is accessible. Assumption: Repository name has been decided. Assumption: Developer has Git installed locally (git --version confirms). Assumption: SSH key or HTTPS credentials are configured for GitHub access. |
| --- | --- |

| OUTPUTS | A GitHub repository exists at https://github.com/{owner}/investsim Two branches exist: main and develop. A .gitignore file is committed based on the Node.js template. A placeholder README.md is committed. The repository is cloned locally and open in VS Code. |
| --- | --- |

## 0.2  Configure VS Code Workspace, ESLint, and Prettier

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 0 · Setup | 0.2 | 0.5 days | Mar 03, 2026 | .vscode/, .eslintrc.js, .prettierrc |

| OBJECTIVE | Establish the code quality toolchain that will enforce the style guide defined in Technical Specification Section 4. Every developer tool configured here will run automatically on every file save, ensuring consistent code style. - Create .vscode/settings.json with format-on-save and ESLint integration - Create .eslintrc.js enforcing ES2022, single quotes, semicolons, no-var, and JSDoc requirements - Create .prettierrc enforcing 2-space indent, single quotes, 100-char line length, trailing commas - Install ESLint and Prettier as dev dependencies - Verify that saving a malformatted JS file triggers automatic correction |
| --- | --- |

| TOOLS | - VS Code — IDE configuration - npm — install eslint, prettier, eslint-config-prettier, eslint-plugin-jsdoc - VS Code extensions: ESLint (Microsoft), Prettier (Prettier.io), GitLens npm install --save-dev eslint prettier eslint-config-prettier eslint-plugin-jsdoc |
| --- | --- |

| AI PROMPTS | Prompt: Generate a complete .eslintrc.js for a vanilla JavaScript ES2022 project. Rules must enforce: no var, const preferred, single quotes, semicolons required, 2-space indent, max line length 100, JSDoc comments required on all functions. Include eslint-plugin-jsdoc and eslint-config-prettier. Export as a CommonJS module. Prompt: Generate a .prettierrc JSON file for a JavaScript project: single quotes, semicolons true, 2-space tabs, 100 char print width, trailing commas in ES5 contexts, bracket spacing true. Prompt: Generate a .vscode/settings.json that enables format-on-save using Prettier as the default formatter, enables ESLint auto-fix on save, and sets the default language for .js files to javascript. |
| --- | --- |

| INPUTS | Assumption: Task 0.1 is complete — repository exists and is cloned locally. Assumption: Node.js is installed locally (node --version confirms v18 or above). Assumption: npm is available. Assumption: VS Code is installed with the ESLint and Prettier extensions. |
| --- | --- |

| OUTPUTS | .eslintrc.js is committed to the repository root. .prettierrc is committed to the repository root. .vscode/settings.json is committed (note: some teams exclude this; for a solo project it is included). package.json exists with eslint and prettier listed as devDependencies. Saving a JS file with style violations automatically corrects them. ESLint reports an error for any function missing a JSDoc header. |
| --- | --- |

## 0.3  Set Up Firebase Project

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 0 · Setup | 0.3 | 1 day | Mar 04, 2026 | Firebase Console, firebase-config.js |

| OBJECTIVE | Create and configure the Firebase project that will serve as the application backend for the v1.0 lifecycle. This task is performed in the Firebase console and produces the configuration object that the application uses to connect to Firebase services. - Create a new Firebase project named investsim (or agreed name) on the Spark (free) tier - Enable Firebase Authentication with Email/Password sign-in provider - Create a Cloud Firestore database in production mode (rules will be written in task 1.7) - Register a web app in the Firebase project to obtain the configuration object - Create js/firebase-config.js to read config values from environment variables - Verify the config connects successfully using a minimal test script |
| --- | --- |

| TOOLS | - Firebase Console (console.firebase.google.com) — project and service configuration - Firebase JavaScript SDK v10 — installed via npm or loaded via CDN for GitHub Pages - VS Code — write firebase-config.js npm install --save-dev firebase |
| --- | --- |

| AI PROMPTS | Prompt: Write a firebase-config.js module for a vanilla JavaScript ES2022 project hosted on GitHub Pages. The module must read all Firebase config values (apiKey, authDomain, projectId, storageBucket, messagingSenderId, appId) from environment variables injected at build time. Export the initialised Firebase app, the Auth instance, and the Firestore instance. Include full JSDoc comments. The file must never contain hardcoded credentials. |
| --- | --- |

| INPUTS | Assumption: A Google account is available to create the Firebase project. Assumption: Task 0.2 is complete — npm and the project structure exist. Assumption: The Firebase Spark free tier is sufficient for development (Auth and Firestore are free up to their generous limits). Assumption: The environment variable injection mechanism (GitHub Actions Secrets) will be configured in task 0.6. |
| --- | --- |

| OUTPUTS | A Firebase project exists with Auth (Email/Password) and Firestore enabled. js/firebase-config.js is written and committed — no credentials are hardcoded. All six Firebase config values are listed in .env.example with placeholder values. A local .env file (gitignored) contains the real values for development use. A minimal test script confirms the Firebase connection initialises without errors. |
| --- | --- |

## 0.4  Configure Firebase Emulator Suite

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 0 · Setup | 0.4 | 1 day | Mar 05, 2026 | firebase.json, .firebaserc |

| OBJECTIVE | Configure the Firebase Local Emulator Suite so that all development and testing runs against local emulated services rather than the live Firebase project. This eliminates development costs, protects live data, and allows Firestore Security Rules to be tested safely. - Install the Firebase CLI - Run firebase init to create firebase.json and .firebaserc - Enable emulators for Authentication and Firestore - Configure firebase-config.js to detect a development environment flag and connect to emulators - Verify the emulator starts and the application connects to it instead of the live project |
| --- | --- |

| TOOLS | - Firebase CLI — firebase init, firebase emulators:start - Terminal — run and monitor the emulator process - Browser DevTools — verify emulator connection in network tab npm install -g firebase-tools firebase login firebase init emulators firebase emulators:start |
| --- | --- |

| AI PROMPTS | Prompt: Update the firebase-config.js module to detect when the app is running in a local development environment (using a build-time flag or localhost check) and connect the Auth and Firestore instances to the Firebase Local Emulator Suite. Auth emulator runs on localhost:9099, Firestore on localhost:8080. The production code path must remain unchanged. Include JSDoc comments. |
| --- | --- |

| INPUTS | Assumption: Task 0.3 is complete — Firebase project exists and firebase-config.js is written. Assumption: Node.js and npm are available. Assumption: Java is installed (required by the Firebase Emulator Suite). Assumption: Port 9099 (Auth) and 8080 (Firestore) are available on the development machine. |
| --- | --- |

| OUTPUTS | firebase.json is committed with emulator configuration for Auth and Firestore. .firebaserc is committed with the project alias. firebase emulators:start launches successfully with both emulators running. The application connects to emulators in development and to live Firebase in production. A npm script "emulate" is added to package.json for convenience. |
| --- | --- |

## 0.5  Create .env.example

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 0 · Setup | 0.5 | 0.5 days | Mar 06, 2026 | .env.example |

| OBJECTIVE | Create the .env.example file that documents every environment variable required by the application, with placeholder values and explanatory comments. This file is committed to the repository and serves as the definitive reference for any developer setting up the project. - Document all Firebase config variables with placeholder values - Document the FMP API key variable - Document OWNER_EMAIL and OWNER_PASSWORD with a clear warning that these are used by the setup script only and must never be committed with real values - Add a comment block at the top explaining how to use the file (copy to .env, fill in values) - Verify .env is in .gitignore and will never be committed |
| --- | --- |

| TOOLS | - VS Code — write .env.example - Git — verify .env is in .gitignore before proceeding |
| --- | --- |

| AI PROMPTS | Prompt: Write a complete .env.example file for a web application that uses Firebase Authentication, Cloud Firestore, and the Financial Modeling Prep API. Include all six Firebase config variables, the FMP API key, an OWNER_EMAIL, and an OWNER_PASSWORD. Each variable must have a placeholder value and an inline comment explaining its purpose. Add a header block explaining that this file should be copied to .env and populated with real values, and that .env must never be committed to version control. |
| --- | --- |

| INPUTS | Assumption: Tasks 0.3 and 0.4 are complete — all required environment variables are known. Assumption: .env is already listed in .gitignore from task 0.1. |
| --- | --- |

| OUTPUTS | .env.example is committed to the repository root with all variables documented. .env (with real values) is confirmed present locally and confirmed absent from git tracking. README.md placeholder updated with a reference to .env.example. |
| --- | --- |

## 0.6  Create GitHub Actions Deployment Workflow

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 0 · Setup | 0.6 | 1 day | Mar 09, 2026 | .github/workflows/deploy.yml |

| OBJECTIVE | Create the CI/CD pipeline that automatically deploys the application to GitHub Pages whenever code is merged to the main branch. The workflow must inject all environment variables from GitHub Actions Secrets so that no credentials appear in the repository. - Create .github/workflows/deploy.yml - Trigger: push to main branch - Steps: checkout, inject secrets as environment variables, deploy to GitHub Pages - Configure all Firebase and FMP secrets in the GitHub repository Settings > Secrets - Verify a test push to main triggers the workflow and deploys successfully |
| --- | --- |

| TOOLS | - GitHub Actions — workflow YAML syntax - GitHub.com Settings > Secrets — store all environment variable values - VS Code — write deploy.yml - GitHub Actions tab — monitor workflow execution and read logs |
| --- | --- |

| AI PROMPTS | Prompt: Write a GitHub Actions workflow YAML file that deploys a vanilla JavaScript static web application to GitHub Pages. The workflow triggers on push to the main branch. It must: check out the repository, inject the following GitHub Secrets as environment variables (list all 6 Firebase variables plus FMP_API_KEY), and deploy the contents of the repository root to GitHub Pages using the actions/deploy-pages action. The workflow must not expose any secret values in logs. Include comments explaining each step. |
| --- | --- |

| INPUTS | Assumption: Task 0.3 is complete — Firebase config values are known and available to store as secrets. Assumption: An FMP API key (Basic free tier) has been obtained from financialmodelingprep.com. Assumption: GitHub Pages is enabled on the repository (Settings > Pages). Assumption: OWNER_EMAIL and OWNER_PASSWORD secrets are NOT added here — they are local-only. |
| --- | --- |

| OUTPUTS | .github/workflows/deploy.yml is committed to the repository. All required secrets are stored in GitHub repository Settings > Secrets. A push to main triggers the workflow successfully. The deployed application is accessible at the GitHub Pages URL. No secret values appear in the workflow run logs. |
| --- | --- |

## 0.7  Run Owner Account Setup Script

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 0 · Setup | 0.7 | 0.5 days | Mar 09, 2026 | scripts/setup-owner.js |

| OBJECTIVE | Write and execute a one-time script that creates the Owner account in Firebase Authentication and sets the owner role custom claim. This is the only account provisioned by the developer — all other accounts are created through the application. The script reads credentials from local environment variables and must never be run against the production Firebase project without explicit intent. - Write scripts/setup-owner.js using the Firebase Admin SDK - Script reads OWNER_EMAIL and OWNER_PASSWORD from local .env - Script creates the user in Firebase Auth - Script sets the custom claim { role: "owner" } on the created user - Script writes a record to the Firestore users collection for the owner - Script is run once and then retained in /scripts for documentation purposes only |
| --- | --- |

| TOOLS | - Firebase Admin SDK — createUser, setCustomUserClaims - Node.js — run the script directly - VS Code — write the script npm install --save-dev firebase-admin node scripts/setup-owner.js |
| --- | --- |

| AI PROMPTS | Prompt: Write a Node.js script using the Firebase Admin SDK that creates a single owner account in Firebase Authentication and sets a custom claim { role: "owner" }. The script must read OWNER_EMAIL and OWNER_PASSWORD from process.env. After creating the Auth user, it must write a document to the Firestore users collection with fields: uid, email, role: "owner", displayName: "Owner", createdAt. The script must log each step clearly and exit with a non-zero code on any error. Include full JSDoc comments. Add a prominent comment warning that this script must only be run once. |
| --- | --- |

| INPUTS | Assumption: Task 0.4 is complete — Firebase emulator is running for local testing. Assumption: OWNER_EMAIL and OWNER_PASSWORD are set in the local .env file. Assumption: firebase-admin is available as a dev dependency. Assumption: A Firebase service account key has been downloaded for Admin SDK use (stored locally only, never committed). |
| --- | --- |

| OUTPUTS | scripts/setup-owner.js is committed to the repository (without credentials). The Owner account exists in Firebase Authentication. The Owner account has the custom claim { role: "owner" }. A users document exists in Firestore for the Owner. The service account key file is confirmed absent from git tracking. |
| --- | --- |

## 0.8  Write Project README

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 0 · Setup | 0.8 | 0.5 days | Mar 10, 2026 | README.md |

| OBJECTIVE | Write the definitive README.md that any developer — or the instructor reviewing the project — can use to understand the application, set it up from scratch, configure environment variables, and deploy it. The README is a living document and will be updated throughout the project. - Project overview: what the application does and who it is for - Prerequisites: Node.js version, Firebase CLI, Git - Setup instructions: clone, npm install, copy .env.example to .env, fill in values - Firebase configuration: project setup, emulator setup, running locally - Deployment: how GitHub Actions deploys to GitHub Pages - Repository structure: description of each directory and key file - Diagram references: note that /docs/diagrams/ contains all Mermaid and SVG diagrams |
| --- | --- |

| TOOLS | - VS Code — write README.md in Markdown - VS Code Markdown Preview — verify rendering |
| --- | --- |

| AI PROMPTS | Prompt: Write a professional README.md for a GitHub-hosted vanilla JavaScript web application called InvestSim. The application is a TSX stock market simulation tool for finance students, built with Firebase Authentication, Cloud Firestore, and the Financial Modeling Prep API, deployed on GitHub Pages. The README must include: project overview, prerequisites (Node.js 18+, Firebase CLI, Git), setup instructions (clone, npm install, .env configuration), Firebase project setup summary, emulator usage, deployment via GitHub Actions, repository directory structure, and a link to /docs/diagrams/ for architecture diagrams. Use clear Markdown headings and code blocks for all commands. |
| --- | --- |

| INPUTS | Assumption: Tasks 0.1 through 0.7 are complete — all setup steps are known and can be accurately documented. Assumption: The GitHub Pages URL is known. Assumption: The diagram files from the Project Plan are already in /docs/diagrams/. |
| --- | --- |

| OUTPUTS | README.md is committed with all sections complete. All commands in the README are verified to work as written. The repository structure section accurately reflects the actual directory layout. |
| --- | --- |

Phase 1 · Authentication 8 tasks · Mar 10 – Mar 16, 2026

## 1.1  Firebase Auth Initialisation

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 1 · Authentication | 1.1 | 0.5 days | Mar 10, 2026 | js/services/auth-service.js |

| OBJECTIVE | Create auth-service.js and implement the foundational functions that initialise Firebase Authentication and expose an auth state listener to the rest of the application. This module is the single point of contact for all authentication operations. - Create js/services/auth-service.js with module header JSDoc comment - Import Auth from firebase-config.js - Implement getAuthState(callback) — attaches onAuthStateChanged listener, returns unsubscribe function - Implement getCurrentUserRole() — reads role custom claim from ID token - Export both functions |
| --- | --- |

| TOOLS | - VS Code — write auth-service.js - Firebase Auth SDK — onAuthStateChanged, currentUser, getIdTokenResult - Firebase Emulator — test auth state changes locally |
| --- | --- |

| AI PROMPTS | Prompt: Write the auth-service.js module for a vanilla JavaScript ES2022 application. Import the Firebase Auth instance from ./firebase-config.js. Implement two exported async functions: (1) getAuthState(callback) — attaches an onAuthStateChanged listener that calls callback with the user object or null, and returns the unsubscribe function; (2) getCurrentUserRole() — gets the current user's ID token result and returns the role custom claim string ("student", "administrator", or "owner"), or null if no user is signed in. Include a JSDoc module header and JSDoc comments on every function. Use const and async/await throughout. |
| --- | --- |

| INPUTS | Assumption: Task 0.3 is complete — firebase-config.js exports the Auth instance. Assumption: Task 0.4 is complete — emulator is available for local testing. |
| --- | --- |

| OUTPUTS | js/services/auth-service.js exists with getAuthState and getCurrentUserRole exported. Both functions have complete JSDoc headers. Manual test confirms getAuthState fires correctly when a test user signs in via the emulator. |
| --- | --- |

## 1.2  Student Self-Registration

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 1 · Authentication | 1.2 | 1 day | Mar 11, 2026 | js/views/auth-view.js, js/services/auth-service.js |

| OBJECTIVE | Implement the complete self-registration flow: the registration form UI, client-side validation, Firebase account creation, role claim assignment, and the Firestore users document write. This is the entry point for all student users. - Add registerUser(email, password, displayName) to auth-service.js - Create the registration form HTML in auth-view.js with fields: display name, email, password, confirm password - Implement client-side validation using validators.js (to be written in task 5.9, stub for now) - On successful Firebase createUser: write users/{uid} document with role: student - Trigger portfolio initialisation (task 1.6) after successful registration - Display plain-language error messages for all Firebase error codes |
| --- | --- |

| TOOLS | - VS Code — write auth-view.js registration form and auth-service.js registerUser - Firebase Auth SDK — createUserWithEmailAndPassword, updateProfile - Firebase Firestore SDK — setDoc for users collection - Firebase Emulator — test registration flow end-to-end |
| --- | --- |

| AI PROMPTS | Prompt: Add a registerUser(email, password, displayName) async function to auth-service.js. The function must: call Firebase createUserWithEmailAndPassword; on success, call updateProfile to set the displayName; write a document to the Firestore users collection at users/{uid} with fields: uid, email, displayName, role: "student", createdAt: serverTimestamp(); return { user, error: null } on success or { user: null, error } on failure. Map Firebase error codes (auth/email-already-in-use, auth/weak-password, auth/invalid-email) to plain English messages. Include JSDoc. Prompt: Write the renderRegistrationForm() function for auth-view.js in vanilla JavaScript ES2022. The function must create and return a DOM fragment containing a registration form with fields for displayName, email, password, and confirmPassword. Each field must have a label, input, and an empty error span below it. Include a submit button. Add a link to the login form. Wire the submit handler to call registerUser from auth-service.js after client-side validation. Show inline error messages on validation failure. On success, call router.navigate("/dashboard"). No framework — pure DOM manipulation. |
| --- | --- |

| INPUTS | Assumption: Task 1.1 is complete — auth-service.js exists with getAuthState and getCurrentUserRole. Assumption: firebase-config.js exports both Auth and Firestore instances. Assumption: validators.js will be a stub initially — full implementation in task 5.9. Assumption: router.js navigate function exists or will be stubbed. |
| --- | --- |

| OUTPUTS | registerUser function is added to auth-service.js with full JSDoc. Registration form renders correctly and all fields validate before submission. A new student account is created in the Firebase Auth emulator on successful submission. A users document is written to Firestore with role: student. Firebase error codes are mapped to plain-language messages visible in the UI. |
| --- | --- |

## 1.3  Login Form

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 1 · Authentication | 1.3 | 0.5 days | Mar 12, 2026 | js/views/auth-view.js, js/services/auth-service.js |

| OBJECTIVE | Implement the login form and the loginUser function. On successful login, retrieve the user's role claim and redirect to the appropriate default route for that role. - Add loginUser(email, password) to auth-service.js - Render login form with email and password fields - On success: get role claim, redirect student → /dashboard, administrator → /admin, owner → /owner - Map Firebase auth errors to plain-language messages - Add a link from login form to registration form |
| --- | --- |

| TOOLS | - VS Code — extend auth-view.js and auth-service.js - Firebase Auth SDK — signInWithEmailAndPassword - Firebase Emulator — test login with accounts created in task 1.2 |
| --- | --- |

| AI PROMPTS | Prompt: Add a loginUser(email, password) async function to auth-service.js. The function must call Firebase signInWithEmailAndPassword, then call getCurrentUserRole() to retrieve the role claim from the token. Return { user, role, error: null } on success or { user: null, role: null, error } on failure. Map auth/user-not-found, auth/wrong-password, and auth/invalid-email to plain English messages. Include JSDoc. Prompt: Write a renderLoginForm() function for auth-view.js. It must render a login form with email and password fields, a submit button, and a link to the registration form. Wire the submit handler to call loginUser from auth-service.js. On success, use the returned role to call router.navigate() to the correct default route: /dashboard for student, /admin for administrator, /owner for owner. Show inline error messages on failure. Pure DOM, no framework. |
| --- | --- |

| INPUTS | Assumption: Task 1.2 is complete — registration creates accounts that can be used to test login. Assumption: Role custom claims are set correctly during registration (role: student). Assumption: The owner account was created in task 0.7 with role: owner. |
| --- | --- |

| OUTPUTS | loginUser function added to auth-service.js with JSDoc. Login form renders, validates, and submits correctly. Successful login redirects to the correct route for each role. Failed login displays a plain-language error message. |
| --- | --- |

## 1.4  Logout

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 1 · Authentication | 1.4 | 0.5 days | Mar 12, 2026 | js/services/auth-service.js, js/components/nav-bar.js |

| OBJECTIVE | Implement the logout function and wire it to the logout button in the nav bar. On logout, clear all local application state and redirect to the login screen. - Add logoutUser() to auth-service.js - Add a logout button to the nav bar (nav-bar.js, to be created in task 2.4 — stub the button for now) - On logout: call Firebase signOut, clear any cached state, redirect to /login |
| --- | --- |

| TOOLS | - VS Code — extend auth-service.js - Firebase Auth SDK — signOut |
| --- | --- |

| AI PROMPTS | Prompt: Add a logoutUser() async function to auth-service.js. The function must call Firebase signOut on the Auth instance, clear any locally cached application state (define a clearAppState() stub that can be expanded later), and return { success: true, error: null } or { success: false, error }. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: Task 1.3 is complete — login works and produces a live auth session. Assumption: nav-bar.js will be completed in task 2.4; a stub logout button is acceptable for now. |
| --- | --- |

| OUTPUTS | logoutUser function added to auth-service.js with JSDoc. Calling logoutUser signs out the Firebase session. After logout, the auth state listener fires with null and the router redirects to /login. |
| --- | --- |

## 1.5  Role Claim Retrieval

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 1 · Authentication | 1.5 | 0.5 days | Mar 13, 2026 | js/services/auth-service.js |

| OBJECTIVE | Verify and harden the getCurrentUserRole function. Ensure it correctly returns the role for all three user types (owner, administrator, student) and gracefully handles edge cases such as a missing claim or an expired token. - Force-refresh the ID token to ensure the most current claims are always returned - Handle the case where the token has no role claim — return null and log a warning - Test with all three account types against the emulator |
| --- | --- |

| TOOLS | - VS Code — refine auth-service.js getCurrentUserRole - Firebase Auth SDK — getIdTokenResult(forceRefresh: true) - Firebase Emulator — create test accounts for all three roles - Browser DevTools Console — verify returned role values |
| --- | --- |

| AI PROMPTS | Prompt: Refine the getCurrentUserRole() function in auth-service.js. It must call getIdTokenResult(true) to force-refresh the token and guarantee the latest custom claims are returned. If the claims object has no role property, log a console warning and return null. Return the role string otherwise. Add error handling for token refresh failures. Update the JSDoc comment to document the force-refresh behaviour and the null return case. |
| --- | --- |

| INPUTS | Assumption: Tasks 1.2 and 1.3 are complete — accounts with role claims exist in the emulator. Assumption: The owner account (task 0.7) has the owner claim set correctly. Assumption: Administrator accounts will be created in task 6.5 — test with owner and student for now. |
| --- | --- |

| OUTPUTS | getCurrentUserRole returns the correct role string for each account type. Returns null and logs a warning when no role claim is present. Force-refresh behaviour is documented in JSDoc. |
| --- | --- |

## 1.6  Portfolio Initialisation on Registration

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 1 · Authentication | 1.6 | 0.5 days | Mar 13, 2026 | js/services/portfolio-service.js |

| OBJECTIVE | Create portfolio-service.js and implement the initPortfolio function that is called immediately after a student successfully registers. This creates the student's portfolio document in Firestore with the $10,000 CAD starting capital. - Create js/services/portfolio-service.js with module header JSDoc - Implement initPortfolio(userId) — creates portfolios/{userId} document - Starting capital value read from constants.js STARTING_CAPITAL constant - Call initPortfolio from registerUser in auth-service.js after successful user creation |
| --- | --- |

| TOOLS | - VS Code — create portfolio-service.js - Firebase Firestore SDK — setDoc - Firebase Emulator — verify document creation |
| --- | --- |

| AI PROMPTS | Prompt: Create portfolio-service.js for a vanilla JavaScript ES2022 application. Import Firestore from firebase-config.js and STARTING_CAPITAL from constants.js. Implement and export initPortfolio(userId) — an async function that creates a document at portfolios/{userId} with fields: userId, startingCapital: STARTING_CAPITAL, capitalBalance: STARTING_CAPITAL, createdAt: serverTimestamp(). Return { success: true, error: null } or { success: false, error }. Include full JSDoc on the module and function. |
| --- | --- |

| INPUTS | Assumption: constants.js exists with STARTING_CAPITAL = 10000 defined. Assumption: firebase-config.js exports the Firestore instance. Assumption: Firestore Security Rules will allow this write — rules are written in task 1.7. |
| --- | --- |

| OUTPUTS | js/services/portfolio-service.js exists with initPortfolio exported. Registering a new student creates a portfolios document in the Firestore emulator. The document contains capitalBalance: 10000 and startingCapital: 10000. |
| --- | --- |

## 1.7  Firestore Security Rules — Authentication Scope

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 1 · Authentication | 1.7 | 0.5 days | Mar 16, 2026 | firestore.rules |

| OBJECTIVE | Write the initial Firestore Security Rules covering the users collection. Students may only read their own document. Administrators may read all user documents. The owner may read and write all. No user may directly write their own role field. - Create firestore.rules with rules_version = "2" - Helper functions: isAuthenticated(), isOwner(), isAdmin(), isStudent(), isOwnerOrAdmin() - users collection: student — read own only; admin — read all; owner — read/write all - Deny direct writes to the role field by students - Test rules using the Firebase emulator Rules Playground |
| --- | --- |

| TOOLS | - VS Code — write firestore.rules - Firebase CLI — firebase emulators:start to test rules - Firebase Console Rules Playground — manual rule testing firebase deploy --only firestore:rules |
| --- | --- |

| AI PROMPTS | Prompt: Write Firestore Security Rules (rules_version 2) for the users collection of an application with three roles stored as custom claims: student, administrator, and owner. Define helper functions for each role check using request.auth.token.role. Rules for the users collection: students may read only their own document (request.auth.uid == userId); administrators may read all user documents but not write; the owner may read and write all documents. Add a comment block at the top of the file explaining the role model and the security boundary principle. |
| --- | --- |

| INPUTS | Assumption: Custom claims are set correctly on all accounts (role: student, administrator, or owner). Assumption: The Firebase emulator is running and connected to the application. |
| --- | --- |

| OUTPUTS | firestore.rules is committed with rules for the users collection. All three role scenarios pass manual testing in the emulator Rules Playground. An unauthorised read (student accessing another student's document) is correctly denied. |
| --- | --- |

## 1.8  Unit Tests — auth-service.js

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 1 · Authentication | 1.8 | 0.5 days | Mar 16, 2026 | tests/auth-service.test.js |

| OBJECTIVE | Write a unit test suite for auth-service.js covering registration, login, logout, and role retrieval. Tests run against the Firebase Auth emulator to avoid hitting the live project. - Test registerUser: success case, duplicate email, weak password - Test loginUser: success with correct role returned, wrong password, unknown email - Test logoutUser: auth state is null after logout - Test getCurrentUserRole: returns correct role for each account type, returns null for missing claim |
| --- | --- |

| TOOLS | - Jest — test runner - Firebase Auth Emulator — test environment npm install --save-dev jest npm test |
| --- | --- |

| AI PROMPTS | Prompt: Write a Jest test suite for auth-service.js. The tests connect to the Firebase Auth emulator running at localhost:9099. Write describe blocks for: registerUser (test success, duplicate email error, weak password error), loginUser (test success returning correct role, wrong password error, user not found error), logoutUser (test that auth state is null after logout), getCurrentUserRole (test owner returns "owner", student returns "student", no claim returns null). Use beforeAll to connect to the emulator and afterEach to clean up created accounts. Include JSDoc on the test file. |
| --- | --- |

| INPUTS | Assumption: Tasks 1.1 through 1.7 are complete. Assumption: Jest is installed as a dev dependency. Assumption: The Firebase Auth emulator is running during test execution. |
| --- | --- |

| OUTPUTS | tests/auth-service.test.js is committed. All tests pass when run with npm test against the emulator. Test coverage report shows all exported functions are exercised. |
| --- | --- |

Phase 2 · Routing 5 tasks · Mar 17 – Mar 20, 2026

## 2.1  Hash-Based Router

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 2 · Routing | 2.1 | 1 day | Mar 17, 2026 | js/router.js |

| OBJECTIVE | Implement the client-side router that maps URL hashes to view modules. The router listens for hashchange events, matches the hash to a registered route, and mounts the corresponding view into the #app container. This is the navigation backbone of the entire application. - Create js/router.js - Implement addRoute(path, viewFn, allowedRoles) — register a route - Implement navigate(path) — programmatically change the hash - Listen for hashchange and popstate events - On navigation: check auth state, check role guard, call viewFn, mount result in #app - Handle unknown routes — redirect to appropriate default |
| --- | --- |

| TOOLS | - VS Code — write router.js - Browser — test hash navigation manually - Browser DevTools — verify DOM mounting and unmounting |
| --- | --- |

| AI PROMPTS | Prompt: Write a client-side hash router in vanilla JavaScript ES2022. The module must export: addRoute(hash, viewFn, allowedRoles) to register routes; navigate(hash) to programmatically navigate; and an init() function that attaches hashchange and popstate listeners and dispatches the current hash on page load. When a hash change occurs: call getCurrentUserRole from auth-service.js, check if the role is in the route's allowedRoles array (redirect to /login if not authenticated, redirect to the role default if unauthorised), then call the viewFn and mount its returned DOM element into document.getElementById("app") after clearing the existing content. Include JSDoc on all exported functions and on the module. |
| --- | --- |

| INPUTS | Assumption: Task 1.5 is complete — getCurrentUserRole is available. Assumption: index.html has a <div id="app"></div> container. Assumption: View functions will be registered in task 2.3 — stubs are sufficient for now. |
| --- | --- |

| OUTPUTS | js/router.js is committed with addRoute, navigate, and init exported. Hash changes mount the correct view into #app. Navigating to an unregistered hash redirects gracefully. All exported functions have JSDoc. |
| --- | --- |

## 2.2  Route Guards by Role

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 2 · Routing | 2.2 | 0.5 days | Mar 18, 2026 | js/router.js |

| OBJECTIVE | Extend the router with the guardRoute function that enforces role-based access control on every navigation event. An unauthenticated user is always redirected to /login. An authenticated user attempting to access a route outside their role is redirected to their role's default route. - Implement guardRoute(requiredRoles, currentRole) as an internal router function - Unauthenticated: redirect to /#/login - Authenticated but wrong role: redirect to role default (student→/dashboard, admin→/admin, owner→/owner) - Test all guard scenarios against the three role types |
| --- | --- |

| TOOLS | - VS Code — extend router.js - Browser DevTools — verify redirect behaviour for each scenario - Firebase Emulator — test with live auth sessions |
| --- | --- |

| AI PROMPTS | Prompt: Add a guardRoute(allowedRoles, currentRole) function inside router.js. The function must: return "allow" if currentRole is in allowedRoles; return "redirect:/login" if currentRole is null (unauthenticated); return "redirect:/dashboard" if currentRole is "student" and not in allowedRoles; return "redirect:/admin" if currentRole is "administrator" and not in allowedRoles; return "redirect:/owner" if currentRole is "owner" and not in allowedRoles. The function is not exported — it is used internally by the router dispatch logic. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: Task 2.1 is complete — router.js exists and dispatches hash changes. Assumption: getCurrentUserRole returns the role string or null. |
| --- | --- |

| OUTPUTS | guardRoute logic is integrated into the router dispatch. All six guard scenarios (3 roles × authenticated/unauthenticated) behave correctly. No route is accessible to an unauthorised role. |
| --- | --- |

## 2.3  Wire All Routes to Views

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 2 · Routing | 2.3 | 0.5 days | Mar 18, 2026 | js/app.js, js/router.js |

| OBJECTIVE | Register all eight application routes in app.js, connecting each hash path to its view module and specifying the allowed roles. View modules will be stubs at this point — the goal is to confirm that navigation works end-to-end before the real views are built. - Register all 8 routes: /login, /register, /dashboard, /trade, /admin, /admin/:userId, /owner - Each route points to a stub view function that renders a placeholder div with the route name - Confirm the router dispatches to the correct stub for each hash - Confirm route guards redirect correctly for each role |
| --- | --- |

| TOOLS | - VS Code — extend app.js with route registrations - Browser — manual navigation testing |
| --- | --- |

| AI PROMPTS | Prompt: Write the route registration section of app.js for an application with these routes: /login (unauthenticated only), /register (unauthenticated only), /dashboard (student), /trade (student), /admin (administrator, owner), /admin/:userId (administrator, owner), /owner (owner only). For each route, call router.addRoute with the path, a stub view function that returns a div with the route name as text content, and the array of allowed roles. Call router.init() after all routes are registered. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: Tasks 2.1 and 2.2 are complete — router.js with guards is ready. Assumption: View modules are stubs — full implementations come in Phases 5 and 6. |
| --- | --- |

| OUTPUTS | All 8 routes are registered in app.js. Navigating to each hash renders the correct stub view. Role guards redirect correctly for all scenarios. |
| --- | --- |

## 2.4  Nav-Bar Component

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 2 · Routing | 2.4 | 0.5 days | Mar 19, 2026 | js/components/nav-bar.js |

| OBJECTIVE | Build the nav-bar component that renders context-appropriate navigation links based on the current user's role. The nav bar is persistent across all authenticated views and includes the logout button. - Create js/components/nav-bar.js - Student nav: Dashboard, Trade - Administrator nav: Students - Owner nav: Students, User Management - All authenticated navs: user display name and Logout button - Wire logout button to logoutUser from auth-service.js |
| --- | --- |

| TOOLS | - VS Code — write nav-bar.js - CSS — style nav bar using css/main.css - Browser — verify render for each role |
| --- | --- |

| AI PROMPTS | Prompt: Write a nav-bar.js component for a vanilla JavaScript ES2022 application. Export a renderNavBar(user, role) function that creates and returns a nav element. The nav must show: for all roles — the app name "InvestSim", the user's displayName, and a Logout button wired to logoutUser(). For student role — add a Dashboard link (/#/dashboard) and a Trade link (/#/trade). For administrator role — add a Students link (/#/admin). For owner role — add Students (/#/admin) and User Management (/#/owner) links. Add tooltip title attributes to each nav item. Include JSDoc on module and function. |
| --- | --- |

| INPUTS | Assumption: Task 1.4 is complete — logoutUser is available in auth-service.js. Assumption: The current user object and role are available when the nav bar is rendered. |
| --- | --- |

| OUTPUTS | js/components/nav-bar.js is committed. The nav bar renders correctly for all three role types. The logout button successfully logs out and redirects to /login. All nav links navigate to the correct hash routes. |
| --- | --- |

## 2.5  Unit Tests — router.js

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 2 · Routing | 2.5 | 0.5 days | Mar 20, 2026 | tests/router.test.js |

| OBJECTIVE | Write a Jest unit test suite for router.js covering route registration, guard logic, and navigation behaviour. Tests mock the auth-service to isolate the router logic. - Test addRoute: route is registered and callable - Test guardRoute: all six scenarios (3 roles × allowed/denied) - Test navigate: hash changes to the expected value - Test unknown hash: redirects to /login |
| --- | --- |

| TOOLS | - Jest — test runner - Jest module mocking — mock auth-service.js getCurrentUserRole |
| --- | --- |

| AI PROMPTS | Prompt: Write a Jest test suite for router.js. Mock auth-service.js so getCurrentUserRole returns a controllable value. Test: addRoute registers a route that can be dispatched; guardRoute returns allow for correct role, redirect:/login for null, redirect to role default for wrong role (test all three wrong-role cases); navigate sets window.location.hash; dispatching an unknown hash redirects to /#/login. Use jest.mock for auth-service and jsdom for the DOM environment. |
| --- | --- |

| INPUTS | Assumption: Tasks 2.1 through 2.4 are complete. Assumption: Jest and jsdom are configured as the test environment. |
| --- | --- |

| OUTPUTS | tests/router.test.js is committed. All tests pass. Guard logic is fully covered with no untested branches. |
| --- | --- |

Phase 3 · Market Data 8 tasks · Mar 23 – Mar 27, 2026

## 3.1  FMP API Client

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 3 · Market Data | 3.1 | 1 day | Mar 23, 2026 | js/services/market-data-service.js |

| OBJECTIVE | Create market-data-service.js and implement the core FMP API client function that fetches a price quote for a given ticker symbol. All requests route through cache-service (task 3.3) — this task establishes the HTTP fetch logic that cache-service calls on a cache miss. - Create js/services/market-data-service.js - Implement getQuote(symbol) — public function, routes through cache - Implement fetchFromFMP(symbol) — private, makes the actual HTTP GET to FMP /api/v3/quote/{symbol} - API key appended as query parameter from environment variable FMP_API_KEY - Parse FMP response — extract symbol, name, price, currency, exchange - Return null and log error on HTTP failure or empty response |
| --- | --- |

| TOOLS | - VS Code — write market-data-service.js - fetch API — native browser HTTP client - FMP API documentation — https://financialmodelingprep.com/developer/docs - Browser DevTools Network tab — inspect FMP API responses |
| --- | --- |

| AI PROMPTS | Prompt: Write market-data-service.js for a vanilla JavaScript ES2022 application. Import cacheService from cache-service.js and FMP_BASE_URL, FMP_API_KEY from constants.js. Implement: (1) an unexported async fetchFromFMP(symbol) function that calls fetch() on the FMP /api/v3/quote/{symbol} endpoint with the API key appended, parses the JSON response array, and returns the first element as a Quote object { symbol, name, price, currency, exchange, delayed: true } or null on error; (2) an exported async getQuote(symbol) function that calls cacheService.getPrice(symbol) first and returns cached data if fresh, otherwise calls fetchFromFMP and writes the result to the cache before returning it. Include full JSDoc on all functions. |
| --- | --- |

| INPUTS | Assumption: A valid FMP Basic tier API key is available in the local .env as FMP_API_KEY. Assumption: cache-service.js will be stubbed or written in task 3.3 — create a stub for now. Assumption: constants.js has FMP_BASE_URL defined as https://financialmodelingprep.com. Assumption: TSX symbols use the .TO suffix (e.g., RY.TO for Royal Bank of Canada). |
| --- | --- |

| OUTPUTS | js/services/market-data-service.js exists with getQuote exported. A manual test call to getQuote("RY.TO") returns a price object from FMP. HTTP errors return null with a console error log. All functions have complete JSDoc. |
| --- | --- |

## 3.2  Instrument Search

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 3 · Market Data | 3.2 | 0.5 days | Mar 24, 2026 | js/services/market-data-service.js |

| OBJECTIVE | Add the searchInstruments function to market-data-service.js. This function calls the FMP /search endpoint and filters results to TSX-listed instruments, returning an array suitable for display in the trade screen search results. - Implement searchInstruments(query) in market-data-service.js - Call FMP GET /api/v3/search?query={query}&limit=10&apikey={key} - Filter results to exchange === "TSX" or symbol ending in ".TO" - Return array of { symbol, name, assetClass, exchange } - Return empty array on error — never throw to the caller |
| --- | --- |

| TOOLS | - VS Code — extend market-data-service.js - FMP /search endpoint — test with a few TSX symbol queries - Browser DevTools Console — inspect returned search results |
| --- | --- |

| AI PROMPTS | Prompt: Add a searchInstruments(query) async function to market-data-service.js. The function must call the FMP /api/v3/search endpoint with the query string and limit=10. Filter the results array to include only instruments where exchangeShortName is "TSX" or the symbol ends with ".TO". Map each result to { symbol, name, assetClass: result.type, exchange: result.exchangeShortName }. Return the filtered array, or an empty array on any error. Never throw. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: Task 3.1 is complete — FMP_BASE_URL, FMP_API_KEY, and the fetch pattern are established. Assumption: FMP Basic tier includes the /search endpoint (it does on the free tier). |
| --- | --- |

| OUTPUTS | searchInstruments is added to market-data-service.js and exported. A test query for "Royal Bank" returns RY.TO in the results. A query with no TSX results returns an empty array without error. |
| --- | --- |

## 3.3  Firestore Price Cache

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 3 · Market Data | 3.3 | 0.5 days | Mar 24, 2026 | js/services/cache-service.js |

| OBJECTIVE | Create cache-service.js with the getPrice and setPrice functions that read from and write to the Firestore priceCache collection. This is the caching layer that limits FMP API calls to within the tier's daily quota. - Create js/services/cache-service.js - Implement getPrice(symbol) — read priceCache/{symbol} from Firestore, return entry or null - Implement setPrice(symbol, priceData) — write priceCache/{symbol} with retrievedAt: serverTimestamp() - Both functions handle Firestore errors gracefully — null on failure, never throw |
| --- | --- |

| TOOLS | - VS Code — write cache-service.js - Firebase Firestore SDK — getDoc, setDoc - Firebase Emulator — test reads and writes to priceCache |
| --- | --- |

| AI PROMPTS | Prompt: Write cache-service.js for a vanilla JavaScript ES2022 application. Import Firestore from firebase-config.js. Implement and export: (1) getPrice(symbol) — an async function that reads the document at priceCache/{symbol} from Firestore and returns the document data object or null if not found or on error; (2) setPrice(symbol, priceData) — an async function that writes priceData merged with { retrievedAt: serverTimestamp() } to priceCache/{symbol} using setDoc with merge: true. Both functions must catch all errors, log them, and return null or resolve silently. Include full JSDoc. |
| --- | --- |

| INPUTS | Assumption: firebase-config.js exports the Firestore instance. Assumption: Firestore Security Rules for priceCache will be written in task 3.6. Assumption: The Firebase emulator is running. |
| --- | --- |

| OUTPUTS | js/services/cache-service.js exists with getPrice and setPrice exported. setPrice writes a document to the emulator priceCache collection. getPrice reads the document back correctly. Errors return null without throwing. |
| --- | --- |

## 3.4  Cache TTL Logic

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 3 · Market Data | 3.4 | 0.5 days | Mar 25, 2026 | js/services/cache-service.js, js/utils/constants.js |

| OBJECTIVE | Add the isCacheFresh function to cache-service.js and create the CACHE_TTL_MS constant in constants.js. The TTL is the single configuration value that controls how frequently prices are refreshed from FMP — 24 hours on the Basic tier, 20 minutes on Premium. - Create js/utils/constants.js with CACHE_TTL_MS, STARTING_CAPITAL, FMP_BASE_URL, and BOND_INSTRUMENTS stub - Set CACHE_TTL_MS = 24 * 60 * 60 * 1000 for the Basic (development) tier - Add isCacheFresh(entry) to cache-service.js — returns true if entry.retrievedAt is within TTL - Integrate isCacheFresh into getPrice — return null if entry is stale so fetchFromFMP is triggered |
| --- | --- |

| TOOLS | - VS Code — create constants.js, extend cache-service.js |
| --- | --- |

| AI PROMPTS | Prompt: Create js/utils/constants.js for a vanilla JavaScript ES2022 project. Export the following constants with JSDoc comments on each: STARTING_CAPITAL = 10000 (CAD, fixed starting capital for all students); CACHE_TTL_MS = 86400000 (24 hours in milliseconds — for Basic FMP tier; comment states: change to 1200000 for Premium tier); FMP_BASE_URL = "https://financialmodelingprep.com/api/v3"; BOND_INSTRUMENTS = [] (empty array stub, to be populated in task 3.5). Add a module-level JSDoc comment. Prompt: Add an isCacheFresh(entry) function to cache-service.js. The function receives a Firestore document data object. It must check if entry.retrievedAt (a Firestore Timestamp) exists and if the number of milliseconds elapsed since retrievedAt.toMillis() is less than CACHE_TTL_MS imported from constants.js. Return true if fresh, false otherwise. Update getPrice to call isCacheFresh and return null if the entry is stale. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: Task 3.3 is complete — cache-service.js exists. Assumption: Firestore Timestamps are stored server-side using serverTimestamp(). |
| --- | --- |

| OUTPUTS | js/utils/constants.js is committed with all constants and JSDoc. isCacheFresh is added to cache-service.js. getPrice returns null for a stale cache entry, triggering a fresh FMP fetch. CACHE_TTL_MS change from 86400000 to 1200000 is documented as the Premium upgrade step. |
| --- | --- |

## 3.5  Bond Fixed-Yield Calculator

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 3 · Market Data | 3.5 | 0.5 days | Mar 25, 2026 | js/services/market-data-service.js, js/utils/constants.js |

| OBJECTIVE | Implement the bond instrument model. Populate BOND_INSTRUMENTS in constants.js with a representative set of fixed-yield bond options. Implement getBondValue in market-data-service.js to calculate a bond position's current value. - Populate BOND_INSTRUMENTS with 4 representative bonds: 3-month, 6-month, 1-year, 2-year Government of Canada equivalents - Each bond: { id, name, termMonths, couponRate, parValue } - Implement getBondValue(position) — calculates accrued interest based on elapsed days - Formula: currentValue = parValue + (parValue × couponRate × daysHeld / 365) |
| --- | --- |

| TOOLS | - VS Code — extend constants.js and market-data-service.js - Browser Console — verify bond value calculations manually |
| --- | --- |

| AI PROMPTS | Prompt: Populate the BOND_INSTRUMENTS array in constants.js with four simplified Government of Canada bond equivalents: (1) id: "BOND-3M", name: "GoC 3-Month T-Bill", termMonths: 3, couponRate: 0.048, parValue: 1000; (2) id: "BOND-6M", name: "GoC 6-Month T-Bill", termMonths: 6, couponRate: 0.049, parValue: 1000; (3) id: "BOND-1Y", name: "GoC 1-Year Bond", termMonths: 12, couponRate: 0.051, parValue: 1000; (4) id: "BOND-2Y", name: "GoC 2-Year Bond", termMonths: 24, couponRate: 0.053, parValue: 1000. Add a JSDoc comment explaining these are simplified educational instruments, not real market instruments. Prompt: Add getBondValue(position) and getBondInstruments() functions to market-data-service.js. getBondInstruments() returns the BOND_INSTRUMENTS array from constants.js. getBondValue(position) calculates current bond value: daysHeld = (Date.now() - position.openedAt.toMillis()) / 86400000; accruedInterest = position.units * position.purchasePricePerUnit * position.couponRate * daysHeld / 365; return position.units * position.purchasePricePerUnit + accruedInterest. Round to 2 decimal places. Include JSDoc on both functions. |
| --- | --- |

| INPUTS | Assumption: Task 3.1 is complete — market-data-service.js structure is established. Assumption: position.openedAt is a Firestore Timestamp with a toMillis() method. Assumption: Representative Canadian bond rates are educational approximations, not live data. |
| --- | --- |

| OUTPUTS | BOND_INSTRUMENTS array in constants.js has 4 bond options with JSDoc. getBondValue and getBondInstruments are exported from market-data-service.js. Manual test confirms a 1-year bond held for 30 days returns a value slightly above par. |
| --- | --- |

## 3.6  Firestore Security Rules — priceCache

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 3 · Market Data | 3.6 | 0.5 days | Mar 26, 2026 | firestore.rules |

| OBJECTIVE | Extend firestore.rules with rules for the priceCache collection. Students and administrators may read cached prices (they need them to display portfolio values) but may not write. Only the owner role may write to the cache (in practice, the write comes from the application itself acting as the current user). - Add priceCache collection rules to firestore.rules - Authenticated users (any role): read allowed - Write: only allowed for authenticated users (the app writes on cache miss) - Re-run emulator rules tests to confirm no regressions from task 1.7 |
| --- | --- |

| TOOLS | - VS Code — extend firestore.rules - Firebase Emulator Rules Playground — test priceCache rules firebase emulators:start --only firestore |
| --- | --- |

| AI PROMPTS | Prompt: Extend the existing firestore.rules file to add rules for the priceCache collection. Authenticated users with any role may read any priceCache document. Authenticated users may write to priceCache (the client app writes on a cache miss). Unauthenticated users may not read or write. Add a comment explaining that write access is granted to all authenticated users because the client-side cache-service writes prices on a cache miss, and that this is acceptable because price data is not sensitive. |
| --- | --- |

| INPUTS | Assumption: Task 1.7 rules for users collection are already in firestore.rules. Assumption: All writes to priceCache come from the application on behalf of an authenticated user. |
| --- | --- |

| OUTPUTS | priceCache rules are added to firestore.rules and committed. Authenticated read of priceCache succeeds in the emulator. Unauthenticated read of priceCache is denied in the emulator. Existing users collection rules still pass. |
| --- | --- |

## 3.7  Unit Tests — cache-service.js

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 3 · Market Data | 3.7 | 0.5 days | Mar 26, 2026 | tests/cache-service.test.js |

| OBJECTIVE | Write a Jest test suite for cache-service.js covering the full cache lifecycle: miss, write, fresh hit, stale hit, and error handling. Tests run against the Firestore emulator. - Test getPrice on empty cache: returns null (cache miss) - Test setPrice then getPrice: returns the written data (cache hit) - Test isCacheFresh with a fresh entry: returns true - Test isCacheFresh with a stale entry (retrievedAt > TTL ago): returns false - Test getPrice with a stale entry: returns null (triggers re-fetch) |
| --- | --- |

| TOOLS | - Jest — test runner - Firestore Emulator — test environment for Firestore reads and writes |
| --- | --- |

| AI PROMPTS | Prompt: Write a Jest test suite for cache-service.js running against the Firestore emulator. Tests must cover: getPrice for a non-existent symbol returns null; setPrice followed by getPrice returns the correct price data; isCacheFresh with a Timestamp from 1 minute ago returns true (TTL is 24 hours); isCacheFresh with a Timestamp from 25 hours ago returns false; getPrice when the cached entry is stale returns null. Use beforeAll to connect to the Firestore emulator and afterEach to clear the priceCache collection. |
| --- | --- |

| INPUTS | Assumption: Tasks 3.3 and 3.4 are complete. Assumption: Firestore emulator is running during test execution. |
| --- | --- |

| OUTPUTS | tests/cache-service.test.js is committed. All cache lifecycle scenarios pass. |
| --- | --- |

## 3.8  Unit Tests — market-data-service.js

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 3 · Market Data | 3.8 | 0.5 days | Mar 27, 2026 | tests/market-data-service.test.js |

| OBJECTIVE | Write a Jest test suite for market-data-service.js. FMP API calls are mocked — tests do not make real HTTP requests. The Firestore cache interaction is tested via the emulator. - Mock fetch to simulate FMP API responses - Test getQuote: cache miss triggers FMP fetch, result cached - Test getQuote: cache hit returns cached data without FMP fetch - Test getQuote: FMP HTTP error returns null - Test searchInstruments: returns filtered TSX results - Test getBondValue: correct calculation for a known input |
| --- | --- |

| TOOLS | - Jest — test runner with fetch mocking (jest.spyOn or jest-fetch-mock) - Firestore Emulator — cache read/write testing |
| --- | --- |

| AI PROMPTS | Prompt: Write a Jest test suite for market-data-service.js. Mock the global fetch function to return controlled FMP API responses. Test: getQuote on cache miss calls fetch and caches the result; getQuote on cache hit returns cached data without calling fetch; getQuote when fetch returns a non-200 status returns null; searchInstruments with a mock response filters to TSX-only results; getBondValue with a known position (1000 units, $10 par, 5% coupon, 365 days held) returns $1,500 (1000 × 10 + 1000 × 10 × 0.05 × 1 = 10500 — adjust formula to match implementation). Include JSDoc on the test file. |
| --- | --- |

| INPUTS | Assumption: Tasks 3.1 through 3.5 are complete. Assumption: jest-fetch-mock or equivalent is installed. |
| --- | --- |

| OUTPUTS | tests/market-data-service.test.js is committed. All tests pass with mocked FMP responses. No real HTTP requests are made during the test run. |
| --- | --- |

Phase 4 · Portfolio Service 7 tasks · Mar 30 – Apr 04, 2026

## 4.1  Execute Buy Transaction

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 4 · Portfolio Service | 4.1 | 1.5 days | Mar 30, 2026 | js/services/portfolio-service.js |

| OBJECTIVE | Implement the executeBuy function in portfolio-service.js. This is the most critical business logic function in the application. It must validate available capital, then execute a Firestore batch write that atomically creates a transaction document, creates a position document, and deducts the cost from the capital balance. - Validate: totalCost = units × pricePerUnit must be <= capitalBalance - Firestore batch write (atomic): write transactions/{auto-id} doc, write positions/{auto-id} doc, update portfolios/{userId} capitalBalance - Transaction doc fields: userId, assetId, assetClass, assetName, type: "buy", units, pricePerUnit, totalValue, timestamp: serverTimestamp() - Position doc fields: userId, assetId, assetClass, assetName, units, purchasePricePerUnit, couponRate (bonds only), totalCost, currentValue: totalCost, status: "open", openedAt: serverTimestamp(), closedAt: null - Return { success: true, positionId } or { success: false, error } on validation failure or Firestore error |
| --- | --- |

| TOOLS | - VS Code — extend portfolio-service.js - Firebase Firestore SDK — writeBatch, collection, doc, serverTimestamp - Firebase Emulator — test buy transactions end-to-end |
| --- | --- |

| AI PROMPTS | Prompt: Add an executeBuy(userId, buyRequest) async function to portfolio-service.js. buyRequest contains: { assetId, assetClass, assetName, units, pricePerUnit, couponRate (optional, for bonds) }. The function must: (1) read the portfolios/{userId} document to get capitalBalance; (2) validate that units * pricePerUnit <= capitalBalance — return { success: false, error: "Insufficient funds" } if not; (3) create a Firestore writeBatch; (4) add a new document to the transactions collection with all required fields; (5) add a new document to the positions collection with status: "open"; (6) update portfolios/{userId} capitalBalance by decrementing by totalCost using FieldValue.increment(-totalCost); (7) commit the batch; (8) return { success: true, positionId } on success or { success: false, error } on Firestore error. All writes must be in the same batch. Include full JSDoc. |
| --- | --- |

| INPUTS | Assumption: Task 1.6 is complete — portfolios documents exist for all student accounts. Assumption: Firestore Security Rules for portfolios will be written in task 4.6. Assumption: The buyRequest object is validated by the trade view before calling executeBuy. Assumption: pricePerUnit is the current market price at the moment of the transaction. |
| --- | --- |

| OUTPUTS | executeBuy is added to portfolio-service.js with full JSDoc. A test buy transaction creates both a transactions and a positions document in the emulator. capitalBalance in the portfolios document is decremented correctly. Attempting a buy that exceeds capital returns { success: false, error: "Insufficient funds" }. All three Firestore writes are atomic — if any fail, none are committed. |
| --- | --- |

## 4.2  Execute Sell Transaction

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 4 · Portfolio Service | 4.2 | 1.5 days | Apr 01, 2026 | js/services/portfolio-service.js |

| OBJECTIVE | Implement the executeSell function. Like executeBuy, this uses a Firestore batch write to atomically create a sell transaction, update the position document, and credit the proceeds to the capital balance. If all units of a position are sold, the position status is set to "closed". - Validate: unitsToSell must be > 0 and <= position.units - Firestore batch write: write transactions/{auto-id} sell doc, update positions/{positionId} units and status, update portfolios/{userId} capitalBalance - If units remaining after sell === 0: set position status to "closed", set closedAt: serverTimestamp() - Proceeds = unitsToSell × currentPrice (current market price at time of sale) - Return { success: true } or { success: false, error } |
| --- | --- |

| TOOLS | - VS Code — extend portfolio-service.js - Firebase Firestore SDK — writeBatch, FieldValue.increment - Firebase Emulator — test sell transactions including full close |
| --- | --- |

| AI PROMPTS | Prompt: Add an executeSell(userId, sellRequest) async function to portfolio-service.js. sellRequest contains: { positionId, assetId, assetClass, assetName, unitsToSell, currentPrice }. The function must: (1) read the positions/{positionId} document to get current units; (2) validate unitsToSell > 0 and unitsToSell <= position.units — return { success: false, error: "Insufficient units" } if not; (3) calculate proceeds = unitsToSell * currentPrice; (4) create a Firestore writeBatch; (5) add a sell transaction document; (6) update the position document: decrement units by unitsToSell; if remaining units === 0 set status: "closed" and closedAt: serverTimestamp(); (7) update portfolios/{userId} capitalBalance with FieldValue.increment(proceeds); (8) commit the batch; (9) return { success: true } or { success: false, error }. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: Task 4.1 is complete — positions documents exist from buy transactions. Assumption: currentPrice is the delayed market price fetched by market-data-service at the moment of sale. Assumption: Partial sells (selling fewer units than held) leave the position open with reduced units. |
| --- | --- |

| OUTPUTS | executeSell is added to portfolio-service.js with JSDoc. A partial sell reduces units and leaves position status as "open". A full sell sets position status to "closed" and sets closedAt. capitalBalance is credited by the correct proceeds amount. Attempting to sell more units than held returns { success: false, error: "Insufficient units" }. |
| --- | --- |

## 4.3  Portfolio Read

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 4 · Portfolio Service | 4.3 | 0.5 days | Apr 01, 2026 | js/services/portfolio-service.js |

| OBJECTIVE | Implement getPortfolio(userId) — reads the portfolio document and computes the total current portfolio value by aggregating all open position values. - Read portfolios/{userId} document - Read all open positions for userId - Fetch current prices for each open position via market-data-service.getQuote - Compute total portfolio value: capitalBalance + sum of all open position current values - Return Portfolio object: { capitalBalance, startingCapital, openPositionValue, totalValue, gainLoss, gainLossPct } |
| --- | --- |

| TOOLS | - VS Code — extend portfolio-service.js - Firebase Firestore SDK — getDoc, query, where |
| --- | --- |

| AI PROMPTS | Prompt: Add a getPortfolio(userId) async function to portfolio-service.js. The function must: (1) read portfolios/{userId} from Firestore; (2) query the positions collection for all documents where userId == userId and status == "open"; (3) for each open position, call market-data-service.getQuote(assetId) or getBondValue(position) for bonds; (4) sum the current values of all open positions; (5) return a Portfolio object: { capitalBalance, startingCapital, openPositionValue, totalValue: capitalBalance + openPositionValue, gainLoss: totalValue - startingCapital, gainLossPct: (gainLoss / startingCapital) * 100 }. Handle cases where a price fetch fails gracefully — use the position's last known value. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: Tasks 4.1 and 4.2 are complete — portfolio, positions, and transaction data exist. Assumption: market-data-service.getQuote is functional. |
| --- | --- |

| OUTPUTS | getPortfolio is exported from portfolio-service.js with JSDoc. Returns correct totals for a student with a mix of open and closed positions. Total value is capitalBalance plus sum of open position current values only. |
| --- | --- |

## 4.4  Transaction History Read

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 4 · Portfolio Service | 4.4 | 0.5 days | Apr 02, 2026 | js/services/portfolio-service.js |

| OBJECTIVE | Implement getTransactions(userId) — retrieves all transaction documents for a given user, sorted by timestamp descending. Used by both the student position detail view and the administrator transaction table. - Query transactions collection where userId == userId, orderBy timestamp descending - Return array of Transaction objects - Support optional positionId filter for position-specific transaction history |
| --- | --- |

| TOOLS | - VS Code — extend portfolio-service.js - Firebase Firestore SDK — query, where, orderBy |
| --- | --- |

| AI PROMPTS | Prompt: Add a getTransactions(userId, positionId = null) async function to portfolio-service.js. The function must query the transactions Firestore collection for all documents where userId == userId, ordered by timestamp descending. If positionId is provided, add a second where clause filtering by positionId. Return the array of transaction data objects, or an empty array on error. Include JSDoc documenting the optional positionId parameter. |
| --- | --- |

| INPUTS | Assumption: Transaction documents have been written by executeBuy and executeSell. Assumption: All transaction documents include a timestamp field for ordering. |
| --- | --- |

| OUTPUTS | getTransactions exported from portfolio-service.js with JSDoc. Returns all transactions for a user, newest first. Filtering by positionId returns only transactions for that position. |
| --- | --- |

## 4.5  Position Value Calculation

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 4 · Portfolio Service | 4.5 | 0.5 days | Apr 02, 2026 | js/services/portfolio-service.js |

| OBJECTIVE | Implement calcPositionValue(position, currentPrice) — a utility function that computes the current value of any position type. Delegates to getBondValue for bond positions, and uses units × currentPrice for all other asset classes. - For assetClass !== "bond": return position.units × currentPrice - For assetClass === "bond": call market-data-service.getBondValue(position) - For closed positions: return the final value at close (totalCost of the sell transactions) |
| --- | --- |

| TOOLS | - VS Code — extend portfolio-service.js |
| --- | --- |

| AI PROMPTS | Prompt: Add a calcPositionValue(position, currentPrice) function to portfolio-service.js (not async — bond calculation is synchronous). The function must: if position.assetClass === "bond", call getBondValue(position) from market-data-service and return the result; otherwise return position.units * currentPrice, rounded to 2 decimal places. If position.status === "closed", return 0 (closed positions have no current market value — their realised value is in the transaction history). Include JSDoc documenting all three cases. |
| --- | --- |

| INPUTS | Assumption: Task 3.5 is complete — getBondValue is available in market-data-service. Assumption: position.assetClass is always one of: equity, etf, crypto, bond. |
| --- | --- |

| OUTPUTS | calcPositionValue exported from portfolio-service.js with JSDoc. Returns correct values for all four asset classes. Returns 0 for closed positions. |
| --- | --- |

## 4.6  Firestore Security Rules — Portfolio Scope

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 4 · Portfolio Service | 4.6 | 0.5 days | Apr 03, 2026 | firestore.rules |

| OBJECTIVE | Extend firestore.rules with rules for the portfolios, positions, and transactions collections. Students may read and write only their own data. No student may directly write to their capitalBalance field — balance changes must come through batch writes that include a valid transaction document. Administrators and owner may read all data. - portfolios: student read/write own only; no direct write to capitalBalance without a transaction - positions: student read/write own only; admin/owner read all - transactions: student read/write own only; admin/owner read all - Test all rules in the emulator — including the capital balance protection |
| --- | --- |

| TOOLS | - VS Code — extend firestore.rules - Firebase Emulator Rules Playground |
| --- | --- |

| AI PROMPTS | Prompt: Extend firestore.rules to add rules for three collections: portfolios, positions, and transactions. For portfolios/{userId}: students may read and write only their own document (request.auth.uid == userId), but a direct write that changes only capitalBalance without a corresponding transaction must be blocked — add a rule that disallows writes where request.resource.data.diff(resource.data).affectedKeys().hasOnly(["capitalBalance"]). Administrators and owner may read all portfolios documents. For positions and transactions: students may read/write documents where userId == request.auth.uid. Administrators and owner may read all. No deletes are permitted on any collection. Add explanatory comments. |
| --- | --- |

| INPUTS | Assumption: Tasks 4.1 through 4.5 are complete — all Firestore write paths are known. Assumption: Tasks 1.7 and 3.6 rules are already in firestore.rules. |
| --- | --- |

| OUTPUTS | Portfolio scope rules added to firestore.rules and committed. Students cannot read or write each other's portfolios, positions, or transactions. Direct capitalBalance modification without a transaction is denied. All existing rules continue to pass. |
| --- | --- |

## 4.7  Unit Tests — portfolio-service.js

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 4 · Portfolio Service | 4.7 | 1 day | Apr 04, 2026 | tests/portfolio-service.test.js |

| OBJECTIVE | Write a comprehensive Jest test suite for portfolio-service.js. This is the most important test suite in the project — it covers the core business logic of the application. Tests run against both the Firestore emulator and mock market data. - Test initPortfolio: document created with correct starting capital - Test executeBuy: success, insufficient funds - Test executeSell: success with partial sell, success with full sell (position closed), insufficient units - Test getPortfolio: correct totals with mix of open and closed positions - Test getTransactions: returns all transactions newest first, filters by positionId - Test calcPositionValue: equity, bond, closed position |
| --- | --- |

| TOOLS | - Jest — test runner - Firestore Emulator — end-to-end portfolio data testing - Jest mocking — mock market-data-service for price quotes |
| --- | --- |

| AI PROMPTS | Prompt: Write a comprehensive Jest test suite for portfolio-service.js. Use the Firestore emulator and mock market-data-service.getQuote to return $100 for all symbols. Test setup: beforeEach creates a test student portfolio with $10,000. Tests must cover: initPortfolio creates document with capitalBalance 10000; executeBuy with 10 units at $50 succeeds, capitalBalance becomes $9,500, position is open; executeBuy with 200 units at $100 fails with "Insufficient funds"; executeSell of 5 units from the previous position succeeds, capitalBalance becomes $9,500 + (5 × $100) = $10,000; executeSell all remaining units closes the position; executeSell more than held fails with "Insufficient units"; getPortfolio returns correct totalValue; getTransactions returns newest first; calcPositionValue returns 0 for a closed position. |
| --- | --- |

| INPUTS | Assumption: Tasks 4.1 through 4.6 are complete. Assumption: Firestore Security Rules allow test writes from the emulator test environment. |
| --- | --- |

| OUTPUTS | tests/portfolio-service.test.js is committed. All business logic scenarios pass. The insufficient funds and insufficient units guard cases are explicitly tested. |
| --- | --- |

Phase 5 · Student Views 9 tasks · Apr 07 – Apr 17, 2026

## 5.1  Student Dashboard View

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 5 · Student Views | 5.1 | 1.5 days | Apr 07, 2026 | js/views/dashboard-view.js, css/dashboard.css |

| OBJECTIVE | Build the student dashboard view — the default landing screen after login. This is the most important screen in the application and must satisfy N11: simple, intuitive, and information-rich without being overwhelming. - Call getPortfolio(userId) on load and display capital balance, open position value, total value, and gain/loss - Display a data delay notice banner prominently - Render the portfolio-table component (task 5.2) below the summary cards - Include a prominent Buy button navigating to /trade - All monetary values formatted with formatCAD from formatters.js - Positive gain/loss shown in green, negative in red |
| --- | --- |

| TOOLS | - VS Code — write dashboard-view.js and dashboard.css - Browser — live preview of dashboard layout - Firebase Emulator — load real portfolio data |
| --- | --- |

| AI PROMPTS | Prompt: Write renderDashboard(userId) for dashboard-view.js in vanilla JavaScript ES2022. The function must: call getPortfolio(userId) from portfolio-service.js; render a summary section with four stat cards: Available Capital (formatCAD(capitalBalance)), Investment Value (formatCAD(openPositionValue)), Total Portfolio Value (formatCAD(totalValue)), and Total Gain/Loss (formatGainLoss(gainLoss) with green colour for positive, red for negative); render a data delay banner: "⚠ Prices shown are delayed up to 20 minutes"; render the result of renderPortfolioTable(positions) from portfolio-table.js; add a Buy button that calls router.navigate("/trade"). Return the complete assembled DOM element. Show a loading state while data is fetching. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: Phase 4 is complete — getPortfolio returns correct data. Assumption: formatCAD and formatGainLoss will be in formatters.js (task 5.8 — stub if needed). Assumption: portfolio-table.js exists as a stub from task 5.2. |
| --- | --- |

| OUTPUTS | dashboard-view.js renders the complete dashboard with real data from the emulator. All four summary cards display correct values. The data delay notice is visible and prominent. The Buy button navigates to /trade. |
| --- | --- |

## 5.2  Portfolio Table Component

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 5 · Student Views | 5.2 | 1 day | Apr 08, 2026 | js/components/portfolio-table.js |

| OBJECTIVE | Build the portfolio-table component that renders all student positions in a structured table. This component is reused in both the student dashboard and the administrator student detail view. - Columns: Asset, Class, Units, Purchase Cost, Current Value, Gain/Loss, Return %, Status, Actions - Each column header has a tooltip explaining the column - Active positions have a green status indicator; closed positions have a grey indicator - Actions column: View button (navigates to position detail), Sell button (only for open positions) - Empty state: display a helpful message when no positions exist - Accept a readOnly parameter — when true, hide the Actions column (for admin view) |
| --- | --- |

| TOOLS | - VS Code — write portfolio-table.js - Browser — test rendering with mock position data |
| --- | --- |

| AI PROMPTS | Prompt: Write a renderPortfolioTable(positions, options = {}) function for portfolio-table.js in vanilla JavaScript ES2022. options can contain: { readOnly: false }. The function must create an HTML table with these columns: Asset (assetName + assetId), Class (assetClass), Units, Purchase Cost (formatCAD(totalCost)), Current Value (formatCAD(currentValue)), Gain/Loss (formatGainLoss(currentValue - totalCost)), Return % (formatPercent((currentValue - totalCost) / totalCost * 100)), Status (green badge "Active" or grey badge "Closed"), Actions (View button + Sell button if status is open and not readOnly). Add title tooltip attributes to each <th>. If positions is empty, return a div with the message "No investments yet. Click Buy to get started." Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: formatCAD, formatGainLoss, formatPercent are available from formatters.js. Assumption: Positions array comes from getPositions(userId) in portfolio-service.js. Assumption: Current values are pre-calculated before passing to the component. |
| --- | --- |

| OUTPUTS | portfolio-table.js renders a complete table for any positions array. Column header tooltips are present on all columns. Active and closed positions are visually distinguished. Empty state renders a helpful message. readOnly mode hides the Actions column. |
| --- | --- |

## 5.3  Position Card Component

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 5 · Student Views | 5.3 | 0.5 days | Apr 09, 2026 | js/components/position-card.js |

| OBJECTIVE | Build the position-card component that shows the detail view for a single position, including all position fields and the transaction history for that position. Accessible from the View button in the portfolio table. - Display all position fields with labels and tooltips - Show a transaction history table for this position (calls getTransactions with positionId filter) - Include a Sell button for open positions (opens trade view pre-loaded with this position) - Include a Back button returning to the dashboard |
| --- | --- |

| TOOLS | - VS Code — write position-card.js - Browser — test with a position from the emulator |
| --- | --- |

| AI PROMPTS | Prompt: Write a renderPositionCard(userId, positionId) async function for position-card.js in vanilla JavaScript ES2022. The function must: fetch the position document from Firestore; fetch transactions for this position using getTransactions(userId, positionId); render a detail card showing all position fields (assetName, assetClass, units, totalCost, currentValue, gain/loss, status, openedAt, closedAt if closed) with label/value pairs and tooltip title attributes on each label; render a transaction history table showing all buy/sell transactions for this position; add a Sell button (only if status is open) that navigates to /#/trade with the positionId as a query parameter; add a Back button that navigates to /#/dashboard. Return the assembled DOM element. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: getTransactions accepts a positionId filter parameter. Assumption: Position documents are accessible in Firestore with proper security rules. |
| --- | --- |

| OUTPUTS | position-card.js renders complete position detail with transaction history. Sell button appears only for open positions. Back button returns to dashboard. All labels have tooltips. |
| --- | --- |

## 5.4  Trade Screen View

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 5 · Student Views | 5.4 | 1.5 days | Apr 14, 2026 | js/views/trade-view.js |

| OBJECTIVE | Build the trade screen — the most complex student-facing view. Students search for an instrument, see the delayed quote, then choose to buy or sell. The buy and sell forms have inline validation and feed into the trade-modal confirmation (task 5.5). - Instrument search input with live results from searchInstruments - Bond instruments appear as a separate pre-populated section below the search (no search needed) - On instrument selection: display quote card with name, symbol, class, price, and delay notice - Buy form: units input, calculated estimated cost, available capital remaining after purchase - Sell form: show student's open positions for this instrument; units-to-sell input - Both forms validate inline before opening the confirmation modal |
| --- | --- |

| TOOLS | - VS Code — write trade-view.js and trade.css - Firebase Emulator — test with real positions and quotes - FMP API — test live search results (Basic tier) |
| --- | --- |

| AI PROMPTS | Prompt: Write renderTradeView(userId, preloadPositionId = null) for trade-view.js in vanilla JavaScript ES2022. The view must contain: (1) a search input that calls searchInstruments on each keystroke (debounced 400ms) and renders results as a clickable list; (2) a bond section showing getBondInstruments() as clickable options; (3) on instrument selection: fetch the quote, render a quote card with assetName, symbol, assetClass, price (formatCAD), and a delay notice; (4) a Buy section: units input, live-calculated estimated cost and remaining capital, submit button that validates with validateUnits then opens renderTradeModal in buy mode; (5) a Sell section: query open positions for this instrument, render a select list, units-to-sell input, proceeds preview, submit button that validates then opens renderTradeModal in sell mode. If preloadPositionId is provided, pre-select that position in the Sell section. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: searchInstruments, getQuote, getBondInstruments are functional. Assumption: trade-modal.js (task 5.5) will be called for confirmation. Assumption: validators.js (task 5.9) is available. |
| --- | --- |

| OUTPUTS | Trade view renders with working search, quote display, buy form, and sell form. Inline validation prevents submission of invalid unit counts. Bond instruments are available without a search. Preloading a positionId pre-selects the correct position in the sell section. |
| --- | --- |

## 5.5  Trade Modal Component

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 5 · Student Views | 5.5 | 1 day | Apr 15, 2026 | js/components/trade-modal.js |

| OBJECTIVE | Build the trade confirmation modal that appears before any buy or sell transaction is executed. The modal shows the full transaction detail and requires explicit confirmation, satisfying requirement UX-04. - Accept a transaction preview object and a mode ("buy" or "sell") - Buy modal: show asset name, units, price per unit, total cost, capital remaining after purchase - Sell modal: show asset name, units to sell, current price, total proceeds, new capital balance - Confirm button calls executeBuy or executeSell, shows loading state, then redirects to dashboard on success - Cancel button dismisses the modal with no action - Show plain-language error message if the transaction fails |
| --- | --- |

| TOOLS | - VS Code — write trade-modal.js - Browser — test modal appearance and both transaction paths |
| --- | --- |

| AI PROMPTS | Prompt: Write renderTradeModal(userId, mode, transactionPreview, onCancel) for trade-modal.js in vanilla JavaScript ES2022. mode is "buy" or "sell". transactionPreview contains all transaction details. The function must: render a modal overlay with a card showing the transaction summary (all fields appropriate to the mode); a Confirm button that disables itself and shows a loading spinner while calling executeBuy or executeSell, then calls router.navigate("/#/dashboard") on success or shows a plain-language error message on failure; a Cancel button that calls onCancel() and removes the modal from the DOM. The modal must be appended to document.body, not to #app. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: executeBuy and executeSell are available from portfolio-service.js. Assumption: The transaction preview is constructed by the trade view before calling the modal. |
| --- | --- |

| OUTPUTS | Trade modal renders correctly for both buy and sell modes. Confirm executes the transaction and redirects to dashboard on success. Cancel dismisses with no side effects. Errors are shown in plain language inside the modal. |
| --- | --- |

## 5.6  Data Delay Notice Banner

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 5 · Student Views | 5.6 | 0.5 days | Apr 16, 2026 | js/components/nav-bar.js or shared component |

| OBJECTIVE | Implement the persistent data delay notice required by FR-MKT-03. The notice must be visible on every screen that displays price data. Implement it as a shared component that can be included in any view. - Create a renderDelayBanner() function that returns a styled banner element - Text: "⚠ Market prices shown are delayed up to 20 minutes. This is a simulation." - Include the banner in: dashboard view, trade view, position card, admin student detail - Style: visually distinct but not alarming — amber/yellow styling is appropriate |
| --- | --- |

| TOOLS | - VS Code — add to a shared component file or nav-bar.js |
| --- | --- |

| AI PROMPTS | Prompt: Write a renderDelayBanner() function in vanilla JavaScript ES2022 that creates and returns a styled div element. The div must display the text: "⚠ Market prices shown are delayed up to 20 minutes. This is a simulation — no real money is involved." Style it with an amber/yellow background, dark text, a warning icon, and small font size. Add a title tooltip: "Prices are sourced from the Financial Modeling Prep API and are delayed by up to 20 minutes." The function should be exported from a shared-components.js file or added to nav-bar.js. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: The banner is a pure UI component with no data dependencies. |
| --- | --- |

| OUTPUTS | renderDelayBanner() is implemented and exported. The banner appears on dashboard, trade, position card, and admin detail views. The banner is styled consistently and visibly. |
| --- | --- |

## 5.7  All Tooltips

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 5 · Student Views | 5.7 | 0.5 days | Apr 16, 2026 | All view and component modules |

| OBJECTIVE | Audit every interactive element and data display column across all views and ensure a tooltip (title attribute) is present and meaningful. This satisfies UX-01 and N11. - Dashboard: all summary card labels, all portfolio table column headers, Buy button - Trade view: search input, each search result, bond instrument options, units input, Buy button, Sell button - Trade modal: Confirm and Cancel buttons - Position card: all field labels - Admin views: all column headers, student list items - Nav bar: all navigation links and logout button |
| --- | --- |

| TOOLS | - VS Code — review and update all view and component files - Browser — hover test each element to verify tooltip appears |
| --- | --- |

| AI PROMPTS | Prompt: Review the following list of interactive elements and data columns in the InvestSim application and provide the recommended tooltip text for each. Format your response as a JavaScript object mapping element identifiers to tooltip strings, suitable for use as title attribute values. Elements: dashboard Available Capital card, dashboard Investment Value card, dashboard Total Portfolio Value card, dashboard Gain/Loss card, portfolio table Asset column header, Class column header, Units column header, Purchase Cost column header, Current Value column header, Gain/Loss column header, Return% column header, Status column header, Actions column header, Buy button, Sell button in table, View button in table, trade screen search input, units to buy input, estimated cost display, capital remaining display, confirm buy button, cancel button, sell units input, proceeds preview, confirm sell button, nav Dashboard link, nav Trade link, nav Logout button. |
| --- | --- |

| INPUTS | Assumption: All view and component files from tasks 5.1 through 5.6 are complete. Assumption: Tooltip text has been reviewed for clarity and plain language. |
| --- | --- |

| OUTPUTS | Every interactive element and data column in the application has a title attribute. Browser hover test confirms tooltips appear on all targeted elements. Tooltip text is plain English and meaningful to a finance student. |
| --- | --- |

## 5.8  Formatters Utility

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 5 · Student Views | 5.8 | 0.5 days | Apr 17, 2026 | js/utils/formatters.js |

| OBJECTIVE | Implement the formatters.js utility module with all four formatting functions used throughout the application. While this is listed late in Phase 5, stubs should have been used in earlier tasks — this task finalises and hardens the implementations. - formatCAD(amount): formats number as "$1,234.56" using Intl.NumberFormat - formatPercent(value): formats as "12.34%" — two decimal places - formatDateTime(timestamp): formats Firestore Timestamp or Date as "Feb 26, 2026 2:45 PM" - formatGainLoss(amount): formats as "+$234.56" (green) or "-$100.00" (red) — returns { text, isPositive } |
| --- | --- |

| TOOLS | - VS Code — write formatters.js - Browser Console — verify formatting output for edge cases (zero, negative, large numbers) |
| --- | --- |

| AI PROMPTS | Prompt: Write js/utils/formatters.js for a vanilla JavaScript ES2022 application. Export four functions with JSDoc: (1) formatCAD(amount) — formats number as Canadian dollar string using new Intl.NumberFormat("en-CA", { style: "currency", currency: "CAD" }) — returns string; (2) formatPercent(value) — formats number as percentage with 2 decimal places and a sign prefix for positive values: "+12.34%" or "-5.67%" — returns string; (3) formatDateTime(timestamp) — accepts a Firestore Timestamp (with .toDate()) or a JS Date, formats as "Feb 26, 2026 2:45 PM" using Intl.DateTimeFormat — returns string; (4) formatGainLoss(amount) — returns { text: formatCAD(Math.abs(amount)) with sign prefix, isPositive: amount >= 0 } — callers use isPositive to apply colour styling. |
| --- | --- |

| INPUTS | Assumption: Firestore Timestamps have a .toDate() method. Assumption: All monetary amounts are numbers in CAD. |
| --- | --- |

| OUTPUTS | js/utils/formatters.js is committed with all four functions and JSDoc. formatCAD(9500) returns "$9,500.00". formatPercent(-5.5) returns "-5.50%". formatGainLoss(-234.56) returns { text: "$234.56", isPositive: false }. All existing views that used stubs are updated to use the real formatters. |
| --- | --- |

## 5.9  Validators Utility

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 5 · Student Views | 5.9 | 0.5 days | Apr 17, 2026 | js/utils/validators.js |

| OBJECTIVE | Implement the validators.js utility module with all four validation functions used in forms throughout the application. Like formatters.js, stubs may have been used in earlier tasks — this task finalises the implementations. - validateEmail(email): RFC 5322-compatible regex check - validatePassword(password): minimum 8 characters, no whitespace - validateDisplayName(name): non-empty, maximum 50 characters - validateUnits(units, max): must be a positive integer, must not exceed max - All functions return { valid: boolean, message: string } — message is plain English |
| --- | --- |

| TOOLS | - VS Code — write validators.js - Browser Console — test edge cases for each validator |
| --- | --- |

| AI PROMPTS | Prompt: Write js/utils/validators.js for a vanilla JavaScript ES2022 application. Export four functions, each returning { valid: boolean, message: string } where message is a plain English explanation shown to users (not technical): (1) validateEmail(email) — use a standard email regex; invalid returns "Please enter a valid email address"; (2) validatePassword(password) — minimum 8 characters, no whitespace; invalid returns the specific problem in plain language; (3) validateDisplayName(name) — non-empty string, max 50 characters; (4) validateUnits(units, max) — must be a positive integer (no decimals), must be <= max; invalid messages distinguish between "must be a positive whole number" and "cannot exceed X units available". All functions include JSDoc. |
| --- | --- |

| INPUTS | Assumption: All forms using validator stubs are updated to use the real validators after this task. Assumption: max parameter in validateUnits is passed as a number. |
| --- | --- |

| OUTPUTS | js/utils/validators.js is committed with all four functions and JSDoc. validateUnits(5.5, 10) returns { valid: false, message: "must be a positive whole number" }. validateUnits(15, 10) returns { valid: false, message: "cannot exceed 10 units available" }. All form validation in the application now uses these functions. |
| --- | --- |

Phase 6 · Admin/Owner 5 tasks · Apr 22 – Apr 24, 2026

## 6.1  Admin Student List View

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 6 · Admin/Owner Views | 6.1 | 1 day | Apr 22, 2026 | js/views/admin-view.js |

| OBJECTIVE | Build the administrator student list view — the default landing screen for administrators. Shows all registered students with their current portfolio summary, and provides navigation to individual student detail views. - Call getAllUsers() filtered to role: student - For each student, show: display name, email, portfolio total value, gain/loss - Include a search/filter input to find students by name or email - Each student row links to the admin student detail view (/admin/:userId) - Read-only throughout — no admin can modify student data |
| --- | --- |

| TOOLS | - VS Code — write admin-view.js - Firebase Emulator — populate with test student accounts |
| --- | --- |

| AI PROMPTS | Prompt: Write renderAdminStudentList() for admin-view.js in vanilla JavaScript ES2022. The function must: call getAllUsers() from auth-service.js and filter to users where role === "student"; for each student call getPortfolio(userId) to get their current total value and gain/loss; render a searchable table with columns: Student Name, Email, Total Portfolio Value, Gain/Loss, and a View button that navigates to /#/admin/{userId}; add a search input above the table that filters rows by display name or email in real time; show a loading state while data fetches; handle the case where a student has no portfolio document yet. Mark the entire view as read-only with a notice banner. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: getAllUsers() returns all Firestore users documents. Assumption: getPortfolio works for any userId, not just the current user. Assumption: Firestore Security Rules allow admin to read all portfolios (task 4.6). |
| --- | --- |

| OUTPUTS | Admin student list renders with all registered students. Portfolio summaries are displayed for each student. Search input filters the list in real time. View button navigates to the student detail view. |
| --- | --- |

## 6.2  Admin Student Detail View

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 6 · Admin/Owner Views | 6.2 | 0.5 days | Apr 22, 2026 | js/views/admin-view.js |

| OBJECTIVE | Build the administrator student detail view that shows a read-only version of a student's portfolio dashboard. This reuses the portfolio-table component with readOnly: true. - Render the student's display name and email as a header - Render the portfolio summary cards (same as student dashboard but read-only) - Render portfolio-table with readOnly: true (no Sell button) - Include a transaction table section (task 6.3) - Include a Back to Students button |
| --- | --- |

| TOOLS | - VS Code — extend admin-view.js - Firebase Emulator — test with a student account that has buy and sell history |
| --- | --- |

| AI PROMPTS | Prompt: Add a renderAdminStudentDetail(adminUserId, studentUserId) async function to admin-view.js. The function must: fetch the student's users document to get displayName and email; call getPortfolio(studentUserId) for summary data; render the same four summary cards as the student dashboard but with a "Read Only" badge visible; render renderPortfolioTable(positions, { readOnly: true }); include a placeholder div for the transaction table (renderAdminTransactionTable will fill this); add a Back button navigating to /#/admin. Include a prominent banner: "Administrator View — Read Only". Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: Task 6.1 is complete — navigation from student list to detail works. Assumption: portfolio-table.js readOnly mode hides the Actions column. Assumption: Security rules allow admin to read student portfolio data. |
| --- | --- |

| OUTPUTS | Admin student detail view renders student portfolio in read-only mode. No Sell or Buy buttons are visible. Read Only banner is prominently displayed. Back button returns to the student list. |
| --- | --- |

## 6.3  Admin Transaction Table

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 6 · Admin/Owner Views | 6.3 | 0.5 days | Apr 23, 2026 | js/views/admin-view.js |

| OBJECTIVE | Add the full transaction history table to the admin student detail view. This table shows every buy and sell transaction the student has made, satisfying N07. - Call getTransactions(studentUserId) to retrieve all transactions - Columns: Date/Time, Asset, Class, Type (Buy/Sell), Units, Price/Unit, Total Value - Buy transactions shown with a green type badge, sell with a red badge - All column headers have tooltips - Empty state message when no transactions exist |
| --- | --- |

| TOOLS | - VS Code — extend admin-view.js - Firebase Emulator — test with student accounts with full transaction history |
| --- | --- |

| AI PROMPTS | Prompt: Add a renderAdminTransactionTable(studentUserId) async function to admin-view.js. The function must call getTransactions(studentUserId), then render an HTML table with columns: Date/Time (formatDateTime(timestamp)), Asset Name, Asset Class, Type (colour-coded badge: green "BUY" or red "SELL"), Units, Price per Unit (formatCAD), Total Value (formatCAD(totalValue)). Add title tooltip attributes to each column header. If the transactions array is empty, show "No transactions recorded yet." Return the table element. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: getTransactions returns all transactions for a userId sorted newest first. Assumption: formatCAD and formatDateTime are available from formatters.js. |
| --- | --- |

| OUTPUTS | Transaction table renders correctly in the admin student detail view. Buy and sell transactions are visually distinguished by badge colour. All column headers have tooltips. Empty state message appears when no transactions exist. |
| --- | --- |

## 6.4  Owner User Management View

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 6 · Admin/Owner Views | 6.4 | 1 day | Apr 24, 2026 | js/views/owner-view.js |

| OBJECTIVE | Build the owner user management view that allows the owner to see all registered users and assign or revoke the Administrator role. This is the only view in the application that modifies user roles. - Display all users in a table: display name, email, role, registered date - Role column shows current role with a change control for non-owner accounts - Owner row is displayed but cannot be modified - Admin assignment: dropdown to change role between student and administrator - Confirmation prompt before any role change - Changes call setUserRole from auth-service.js (task 6.5) |
| --- | --- |

| TOOLS | - VS Code — write owner-view.js - Firebase Emulator — test role changes with multiple accounts |
| --- | --- |

| AI PROMPTS | Prompt: Write renderOwnerUserManagement() for owner-view.js in vanilla JavaScript ES2022. The function must: call getAllUsers() from auth-service.js; render a table with columns: Display Name, Email, Role (badge), Registered Date, Actions; for users with role "student" or "administrator", show a role selector (dropdown with options "student" and "administrator") and a Save button; for users with role "owner", show only a locked badge with no controls; the Save button must show a browser-native confirm dialog: "Change {displayName}'s role to {newRole}?" and only proceed if confirmed; on confirmation call setUserRole(userId, newRole) from auth-service.js and refresh the table. Include JSDoc. |
| --- | --- |

| INPUTS | Assumption: getAllUsers returns all users including owner — the owner row must be protected in the UI. Assumption: setUserRole is implemented in task 6.5. Assumption: Security rules ensure only the owner can call setUserRole. |
| --- | --- |

| OUTPUTS | Owner user management view renders all registered users. Role selector appears for non-owner accounts. Confirmation dialog appears before any role change. Owner account row shows a locked badge with no controls. |
| --- | --- |

## 6.5  Role Assignment Function

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 6 · Admin/Owner Views | 6.5 | 0.5 days | Apr 24, 2026 | js/services/auth-service.js |

| OBJECTIVE | Implement setUserRole(userId, role) in auth-service.js. This function writes the new role to the Firestore users document. Because custom claims cannot be set client-side (they require the Admin SDK), the application uses a Firestore-based approach: the role is written to Firestore, and the user's next login will pick up the updated claim from their users document. - Write the new role to users/{userId}.role in Firestore - Document the limitation: the new role takes effect on the user's next login (token refresh) - Add a UI notice in the owner view: "Role changes take effect when the user next logs in" - Only callable by the owner — Firestore Security Rules enforce this |
| --- | --- |

| TOOLS | - VS Code — extend auth-service.js - Firebase Firestore SDK — updateDoc |
| --- | --- |

| AI PROMPTS | Prompt: Add a setUserRole(userId, role) async function to auth-service.js. The function must: validate that role is one of "student" or "administrator" — reject "owner" to prevent privilege escalation; call updateDoc on users/{userId} setting the role field to the new value; return { success: true, error: null } on success or { success: false, error } on failure. Add a prominent JSDoc note: "Custom claims cannot be updated client-side. This function updates the Firestore role field. The updated role is read from Firestore on next login via getCurrentUserRole. The Firebase ID token claim is NOT immediately updated." |
| --- | --- |

| INPUTS | Assumption: Firestore Security Rules (task 4.6) allow only the owner to write role fields. Assumption: getCurrentUserRole reads from the Firestore users document as well as the token claim — update this function to fall back to Firestore if needed. Assumption: The role change taking effect on next login is acceptable for this use case. |
| --- | --- |

| OUTPUTS | setUserRole is added to auth-service.js and exported. Role field in Firestore users document is updated correctly. Attempting to set role to "owner" returns an error. Owner view displays a notice about the next-login requirement. |
| --- | --- |

Phase 7 · Testing 8 tasks · Apr 28 – May 05, 2026

## 7.1  Integration Testing — Student Flows

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 7 · Testing & Deployment | 7.1 | 1.5 days | Apr 28, 2026 | Manual test, all student-facing modules |

| OBJECTIVE | Execute a complete end-to-end manual test of all student user stories against the Firebase emulator. Every user story defined in the requirements must pass before proceeding to deployment. - Register a new student account — verify portfolio created with $10,000 - Login — verify redirect to dashboard, verify all summary cards show correct values - Search for a TSX equity — verify results appear, select one, verify quote displays - Buy 10 shares — verify confirmation modal, verify capital deducted, verify position appears in dashboard - Buy a bond instrument — verify bond appears in portfolio with correct value - Sell 5 shares of the equity — verify partial sell, verify capital credited, position still open - Sell remaining shares — verify position closes, status changes to Closed - View position detail — verify transaction history shows all buy and sell events - Verify data delay banner appears on all price-displaying screens - Logout — verify redirect to login, verify session is cleared |
| --- | --- |

| TOOLS | - Browser — Chrome, primary test browser for this task - Firebase Emulator — all tests against emulator - Browser DevTools — inspect network requests, console for errors - Notepad or test log — record pass/fail for each scenario |
| --- | --- |

| AI PROMPTS | No AI prompts for this task — integration testing requires human judgment and real browser interaction. |
| --- | --- |

| INPUTS | Assumption: Phases 0 through 6 are complete. Assumption: Firebase emulator is running with Auth and Firestore. Assumption: FMP API key is valid for Basic tier searches and quotes. |
| --- | --- |

| OUTPUTS | All student flow scenarios pass manual testing. A test log documents each scenario with pass/fail result. Any bugs discovered are fixed before proceeding to task 7.2. No JavaScript console errors during any tested flow. |
| --- | --- |

## 7.2  Integration Testing — Admin and Owner Flows

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 7 · Testing & Deployment | 7.2 | 1 day | Apr 29, 2026 | Manual test, all admin/owner-facing modules |

| OBJECTIVE | Execute end-to-end manual testing of all administrator and owner user stories. - Owner login — verify redirect to /owner, verify user management view loads - Owner assigns admin role to a student — verify confirmation, verify role change in Firestore - Newly promoted admin logs in — verify redirect to /admin, verify student list loads - Admin views a student portfolio — verify read-only dashboard, no Buy/Sell buttons - Admin views student transaction history — verify all transactions appear - Verify student cannot access /admin or /owner — verify redirect to /dashboard - Verify admin cannot access /owner — verify redirect to /admin - Owner revokes admin role — verify user returns to student access on next login |
| --- | --- |

| TOOLS | - Browser — two browser profiles or incognito windows for simultaneous role testing - Firebase Emulator - Test log — record pass/fail for each scenario |
| --- | --- |

| AI PROMPTS | No AI prompts required — human judgment and cross-role testing required. |
| --- | --- |

| INPUTS | Assumption: Task 7.1 student flows all pass. Assumption: The owner account from task 0.7 is functional. Assumption: At least two student accounts have buy/sell transaction history from task 7.1 testing. |
| --- | --- |

| OUTPUTS | All admin and owner flow scenarios pass manual testing. Route guards correctly prevent access across role boundaries. Role assignment and revocation work as expected. Test log documents each scenario. |
| --- | --- |

## 7.3  Cross-Browser Testing

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 7 · Testing & Deployment | 7.3 | 1 day | Apr 30, 2026 | Manual test, all views |

| OBJECTIVE | Test the complete application in the four required browsers — Chrome, Firefox, Safari, and Edge — verifying that all views render correctly and all functionality works. Focus on layout, CSS compatibility, and JavaScript API compatibility. - Test student registration, login, dashboard, trade, position detail in each browser - Test admin student list and detail in each browser - Verify fonts, colours, and layout are consistent across browsers - Verify date formatting (Intl.DateTimeFormat) works correctly in each browser - Verify the Firebase Auth emulator connection works in each browser - Document any browser-specific issues and fix before proceeding |
| --- | --- |

| TOOLS | - Chrome (current version) - Firefox (current version) - Safari (current version — macOS or iOS) - Edge (current version) - Browser DevTools in each browser for console error inspection |
| --- | --- |

| AI PROMPTS | Prompt: The following JavaScript features are used in the InvestSim application: ES2022 modules, async/await, optional chaining, Intl.NumberFormat with CAD currency, Intl.DateTimeFormat, fetch API, localStorage, CSS custom properties, CSS Grid, CSS Flexbox. List any known compatibility issues with current versions of Chrome, Firefox, Safari, and Edge, and recommend any polyfills or workarounds required. |
| --- | --- |

| INPUTS | Assumption: Tasks 7.1 and 7.2 pass in Chrome. Assumption: Safari is available on macOS or iOS for testing. Assumption: Current browser versions are being tested — no legacy browser support is required. |
| --- | --- |

| OUTPUTS | All four browsers render the application correctly. No JavaScript errors in any browser console. Any browser-specific CSS issues are fixed. Cross-browser test log is documented. |
| --- | --- |

## 7.4  Responsive Layout Testing

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 7 · Testing & Deployment | 7.4 | 0.5 days | May 01, 2026 | Manual test, all CSS files |

| OBJECTIVE | Verify that the application is usable and correctly laid out at tablet (768px) and desktop (1024px+) screen widths, as required by UX-06. - Test all views at 768px width (tablet) using browser DevTools device simulation - Test all views at 1280px width (desktop) - Verify tables do not overflow at tablet width — horizontal scroll or column hiding is acceptable - Verify the nav bar is usable at both widths - Fix any layout overflow or text truncation issues |
| --- | --- |

| TOOLS | - Chrome DevTools Device Mode — simulate tablet and desktop widths - VS Code — fix CSS issues |
| --- | --- |

| AI PROMPTS | Prompt: Review the portfolio table component which has 9 columns: Asset, Class, Units, Purchase Cost, Current Value, Gain/Loss, Return%, Status, Actions. Recommend which columns should be hidden at 768px tablet width to prevent overflow, and provide the CSS media query to implement this. Prioritise showing: Asset, Current Value, Gain/Loss, Status, and Actions. Hide: Class, Units, Purchase Cost, Return%. |
| --- | --- |

| INPUTS | Assumption: Tasks 7.1, 7.2, and 7.3 are complete. Assumption: The application is not required to work on mobile (< 768px). |
| --- | --- |

| OUTPUTS | All views are usable and correctly laid out at 768px and 1280px. No horizontal overflow occurs at 768px. Responsive CSS is committed and tested. |
| --- | --- |

## 7.5  Firestore Security Rules Validation

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 7 · Testing & Deployment | 7.5 | 0.5 days | May 01, 2026 | firestore.rules, tests/firestore-rules.test.js |

| OBJECTIVE | Run a comprehensive validation of all Firestore Security Rules using the Firebase emulator. Every access control scenario defined in Technical Specification Section 6.4 must pass. - Write a formal Firestore Rules test file using @firebase/rules-unit-testing - Test all collections: users, portfolios, positions, transactions, priceCache - Test all roles: unauthenticated, student, administrator, owner - Test read, write, and delete for each collection/role combination - The capital balance direct-write protection rule must be explicitly tested |
| --- | --- |

| TOOLS | - @firebase/rules-unit-testing — formal rules test framework - Jest — test runner - Firebase Emulator npm install --save-dev @firebase/rules-unit-testing |
| --- | --- |

| AI PROMPTS | Prompt: Write a complete Firestore Security Rules test suite using @firebase/rules-unit-testing and Jest. The suite must test the following matrix for the users, portfolios, positions, transactions, and priceCache collections: unauthenticated user (read denied, write denied for all); student (read own, write own, read other denied); administrator (read all, write denied); owner (read all, write all). Additionally test: student cannot write directly to capitalBalance in portfolios; student cannot delete any document; owner can write priceCache. Include beforeAll to load firestore.rules and afterAll to clean up. |
| --- | --- |

| INPUTS | Assumption: All security rules from tasks 1.7, 3.6, and 4.6 are in firestore.rules. Assumption: The Firebase emulator is running during test execution. |
| --- | --- |

| OUTPUTS | tests/firestore-rules.test.js is committed. All access control scenarios pass. The capital balance protection rule is tested and passing. All 25+ rule scenarios in the access control matrix are covered. |
| --- | --- |

## 7.6  Deploy to GitHub Pages

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 7 · Testing & Deployment | 7.6 | 0.5 days | May 04, 2026 | GitHub Actions, GitHub Pages |

| OBJECTIVE | Execute the first production deployment of the application to GitHub Pages. Verify the live deployment works end-to-end with the real Firebase project (not the emulator) and the real FMP Basic tier API key. - Merge develop branch to main via a pull request - Verify GitHub Actions workflow triggers and completes successfully - Access the GitHub Pages URL and verify the application loads - Register a test student account on the live deployment - Execute a test buy and sell transaction against live Firebase and live FMP data - Verify the data delay notice is visible and prices reflect real TSX data - Verify the owner account can log in and access the owner view |
| --- | --- |

| TOOLS | - GitHub.com — pull request, Actions tab monitoring - Browser — test live deployment - Firebase Console — verify live Auth and Firestore data |
| --- | --- |

| AI PROMPTS | No AI prompts required — deployment is a manual verification process. |
| --- | --- |

| INPUTS | Assumption: All tasks 7.1 through 7.5 are complete and pass. Assumption: GitHub Actions secrets are configured with live Firebase and FMP Basic API key values. Assumption: Firebase Security Rules are deployed to the live project (not just the emulator). Assumption: The live Firebase project has been configured identically to the emulator setup. |
| --- | --- |

| OUTPUTS | The application is live at the GitHub Pages URL. A test student account registers and completes a buy/sell cycle on the live deployment. No console errors on the live deployment. Firebase Console shows the test account and transactions in the live Firestore. |
| --- | --- |

## 7.7  Upgrade FMP API Key to Premium

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 7 · Testing & Deployment | 7.7 | 0.5 days | May 04, 2026 | constants.js, GitHub Actions Secrets |

| OBJECTIVE | Upgrade the FMP API tier from Basic (end-of-day, 250 calls/day) to Premium ($59/month, 750 calls/minute, intraday data) for classroom deployment. This is a configuration-only change — no code changes are required beyond updating one constant and two secrets. - Subscribe to FMP Premium tier and obtain the Premium API key - Update CACHE_TTL_MS in constants.js from 86400000 (24 hours) to 1200000 (20 minutes) - Update the FMP_API_KEY secret in GitHub Actions Secrets to the Premium key - Update the local .env file with the Premium key - Trigger a redeployment by merging the constants.js change to main - Verify live prices are now intraday (will show different values from end-of-day) |
| --- | --- |

| TOOLS | - FMP website — purchase Premium subscription - GitHub.com — update Actions Secret - VS Code — update constants.js |
| --- | --- |

| AI PROMPTS | No AI prompts required — this is a configuration and billing task. |
| --- | --- |

| INPUTS | Assumption: Task 7.6 deployment is live and functioning on Basic tier. Assumption: The $59/month cost has been approved. Assumption: FMP Premium tier includes TSX intraday delayed data (confirmed in PRE-01 research). |
| --- | --- |

| OUTPUTS | CACHE_TTL_MS is updated to 1200000 and committed. FMP Premium API key is stored in GitHub Actions Secrets. Live deployment uses the Premium key and returns intraday prices. Cache refreshes every 20 minutes, satisfying FR-MKT-02. |
| --- | --- |

## 7.8  Final README Review

| Phase | WBS ID | Duration | Scheduled Due | Module(s) |
| --- | --- | --- | --- | --- |
| Phase 7 · Testing & Deployment | 7.8 | 0.5 days | May 05, 2026 | README.md |

| OBJECTIVE | Conduct a final accuracy review of README.md and all documentation. Verify every command, URL, and instruction is correct and reflects the final deployed state of the application. Update for the Premium FMP tier upgrade. - Verify all commands in the README execute correctly from a clean clone - Update the GitHub Pages URL to the actual live URL - Update the FMP tier section to document both Basic (development) and Premium (classroom) configurations - Add a section documenting the v2.0 roadmap items for future reference - Verify all links to /docs/diagrams/ resolve correctly on GitHub - Perform a final spell-check and grammar review |
| --- | --- |

| TOOLS | - VS Code — edit README.md - GitHub.com — verify rendered Markdown and diagram links - Terminal — verify all documented commands from a fresh clone |
| --- | --- |

| AI PROMPTS | Prompt: Review the following README.md for a GitHub-hosted web application and identify any sections that are likely to be out of date after a project is deployed. Specifically look for: placeholder URLs, development-only instructions that should be marked as such, missing production configuration steps, and any instructions that assume emulator use when the live Firebase project is now in use. Provide a list of sections to review and what to check in each. |
| --- | --- |

| INPUTS | Assumption: Task 7.7 (Premium upgrade) is complete — README must document the Premium configuration. Assumption: The GitHub Pages live URL is known. Assumption: All diagrams in /docs/diagrams/ are committed and render on GitHub. |
| --- | --- |

| OUTPUTS | README.md is accurate, complete, and reflects the deployed state. All commands in the README execute correctly. GitHub Pages URL is correct and live. FMP Basic and Premium configurations are both documented. v2.0 roadmap section is present. The project is ready for classroom use. |
| --- | --- |